## 1. Instructions
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Instructions RFP Number: MMG050725_Inspection Services
Please read the following instructions carefully before responding to this RFP
Proprietary and Confidential: This RFP ("Request for Proposal") and information contained therein is not for use or disclosure outside of Troy Cablevision, Inc., d/b/a C Spire, its affiliates, and third party representatives, and Respondent, except under written agreement by the contracting Parties
Project Background | - Troy Cablevision, Inc. d/b/a C Spire ("C Spire") is the recipient of a Federal grant award, being NTIA Award No. 28-40-MM712, from the U.S. Department of Commerce (“DOC”), National Telecommunications and Information Agency (“NTIA”), under the Enabling Middle Mile Broadband Infrastructure Grant ("MMG") Program Funding Opportunity Number NTIA-MMG-202, for its NTIA Connect Alabama Project. - Pursuant to the terms and conditions of its Federal award, C Spire proposes to build and operate the Connect Alabama Network for 677.1 route miles: 411.5 route miles for access to unserved area, 29.8 route miles for access to underserved areas, and 235.8 route miles for connectivity to 4 Internet peering points. - The entire proposed route will be buried fiber in conduit of at least 144 count fiber. Aerial construction will be considered in areas where topography, wetlands, constructability, or other unforeseen factors dictate. - The Connect Alabama Network aligns well with NTIA's MMG Program's priorities, including: providing symmetrical 1 Gig services to anchor institutions within 1000 feet of the route while also offering fiscally sustainable middle mile; providing non-discriminatory interconnection to last mile broadband providers, with documented interest from 2 last mile providers; and benefiting national security interests for fiber broadband connectivity along the route. - The Connect Alabama Network affords redundancy (preventing a single point of failure), high reliability, and high-speed broadband throughout the 26 unserved/underserved Alabama counties it traverses and enables open access to last mile providers, electrical cooperatives, military facilities, and the Poarch Band of Creek Indians tribal headquarters along its path. - The Connect Alabama Network proposes to support wholesale and retail broadband services throughout the life of the Connect Alabama Project. - The Connect Alabama Project cannot begin construction until its Environmental Assessment receives a Finding Of No Significant Impact ("FONSI"). The FONSI is expected to be received by C Spire for the Connect Alabama Project within ninety (90) days of release of this RFP.
RFP Scope | The purpose of this RFP is to select a qualified supplier to provide independent inspection services for telecom network construction projects. The scope includes oversight and validation of construction quality, adherence to design specifications, safety compliance, and documentation during the rollout of fiber optic and/or wireless networks
This spreadsheet consists of the below tabs:
Tabs |  | Description | Action Needed
1. Instructions |  | Provides general instructions to the Respondent for this RFP | Information Only
2. Questionnaire |  | Contains questions to gather relevant information from the Respondent about itself and its operations | Respondent to Complete
3. Construction Details |  | Contains details about the construction activities and segments | Information Only
4. Inspector Guidelines |  | Contains guidelines for inspectors | Information Only
5. Photo Guidelines |  | Contains guidelines for photo submission | Information Only
6. Pricing Sheet |  | Provides a form for Respondent to input its pricing proposal | Respondent to Complete
7. Vendor Registration |  | Provides a form for Respondent to input its Vendor Registration Setup details | Respondent to Complete
8. Grant Provisions |  | Contains a list of Federal grant related requirements that the Respondent is expected to adhere | Respondent to Complete
9. Subcontractor Reporting |  | Provides a form for Respondent to input required reporting data for C Spire's Connect Alabama Project | Respondent to Complete
10. Workforce Reporting |  | Provides a form for Respondent to input required workforce related reporting data for C Spire's Connect Alabama Project | Information Only, Awarded Contractor(s) to Complete
11. Evaluation Criteria |  | Contains the scoring criteria that C Spire will utilize to fairly and effectively evaluate and rate each Respondent Proposal | Information Only
12. Aerial - Daily Report |  | Provides a report template for respondent to provide daily Aerial job reporting data for C Spire's Connect Alabama Project | Information Only, Awarded Contractor(s) to Complete
13. UG - Daily Report |  | Provides a report template for respondent to provide daily Underground job reporting data for C Spire's Connect Alabama Project | Information Only, Awarded Contractor(s) to Complete
14. Aerial Inspection Report |  | Provides a Inspection report template for respondent to provide Aerial Inspection report for C Spire's Connect Alabama Project | Information Only, Awarded Contractor(s) to Complete
15. UG Inspection Report |  | Provides a Inspection report template for respondent to provide Underground Inspection report for C Spire's Connect Alabama Project | Information Only, Awarded Contractor(s) to Complete
16. Damage Reporting Form |  | Provides a damage reporting template for respondent to provide damage reporting data for C Spire's Connect Alabama Project | Information Only, Awarded Contractor(s) to Complete
17. Signature Page |  | Provides a Certification form for Respondent to input required signatures related to this RFP Response | Respondent to Complete
Below is the RFP timeline:
Activity |  |  | Due Date (EOD)
Intent to Bid response |  |  | 05/07/2025 - 06/06/2025
Non-Disclosure Agreement |  |  | 05/07/2025 - 06/06/2025
Request for Proposal (RFP) Publication |  |  | 2025-05-07
Deadline for Respondent to submit questions (Respondents must send all the questions via email) |  |  | 2025-05-29
Response to Respondent questions due |  |  | 2025-06-02
Deadline for Respondent to submit electronic proposal responses for RFP by 11:59pm Central Time (Late proposals will not be accepted or reviewed) |  |  | 2025-06-09
Bid Award Notification(s) |  |  | 2025-06-14
Deadline for Construction Inspection Service Agreement and Certificate of Insurance |  |  | 2025-06-24
Please read the following instructions carefully:
RFP documents are posted on our website at www.cspire.com. Respondents with valid Intent to Bid and Non-disclosure Agreements with our grants department, will receive an email with additional proprietary information. All correspondence related to Request for Proposals, questions and support documentation MUST be sent to the following email address: tc-grantsupport@cspire.com.
RFP Evaluation, Withdrawal and Award |  | All qualified Proposals will be evaluated and an award made, in C Spire's sole discretion, to the Respondent or Respondents whose Proposal(s) fulfill the Scope of Work; meets the stated budget parameters; contains the Proposal requirements outlined in this RFP; and satisfies the schedule requirements. C Spire reserves the right to select any Proposal deemed to be in the best interest of C Spire. Further, C Spire reserves the right to reject any or all Proposals and/or to waive any and all technical defects in the execution of and informalities in the submission of any Proposal, if determined by C Spire to be in C Spire's best interest. No Proposal may be withdrawn for 90 calendar days after the Proposal Due Date. C Spire is under no obligation to review, negotiate or accept any Proposal.
Respondent Obligation Related to this RFP |  | By responding to this RFP, each Respondent agrees never to claim, file a cause of action, or otherwise assert that C Spire is responsible or liable in any manner or under any theory of liability for any risks, costs, losses, damages, or expenses incurred by said Respondent in connection with this RFP or any Proposal submitted thereby.
No C Spire Commitment |  | This RFP in no way obligates C Spire to enter into a business arrangement with any Respondent nor does it require C Spire to respond to any status request from a Respondent related to its Proposal(s). C Spire shall not be obligated to explain the results of the selection process to any Respondent. Evaluation Criteria for selection of the successful Respondent are as C Spire deems appropriate for the requirement. No specific details of the selection process will be given other than the Evaluation Criteria included with this RFP, nor will any information be given to a Respondent regarding another Respondent’s Proposal. Information such as the successful Respondent’s name, price, terms and conditions, and all data pertinent to the negotiation are considered confidential and proprietary information and shall not be provided to unsuccessful Respondents. By responding to this RFP, each Respondent agrees that C Spire has neither incurred any obligation nor made any commitment to said Respondent in connection with its Proposal.
Requirement for Complete Response |  | Responses to this RFP may not be conditional, incomplete, or contain any alterations from the forms provided. No defects or irregularities of any kind will be accepted.
Proposal Validity Time Requirements |  | Each Respondent's Proposal must acknowledge and provide that the pricing terms included in the Proposal may not be modified for a period not less than 90 days from the Proposal Due Date, and that, if said Proposal is accepted by C Spire, then the pricing terms included therein will be valid for a two year term from the date of the executed Master Services Agreement entered into between Respondent and C Spire in connection with the accepted Proposal.
Fairness |  | To maintain fairness for all Respondents submitting a Proposal, any attempts to contact C Spire staff regarding this RFP outside of the designated email address provided with this RFP shall be grounds for rejection of your Proposal.
Master Servcies Agreement, Definitions and Addendum |  | All Respondents are responsible for reviewing the sample Master Services Agreement associated with this RFP. Any terms not specifically defined in this RFP, shall have the meaning set forth in the sample Master Services Agreement. Upon successful award the Master Service Agreement,and Certificate of Insurance must be executed and submitted be the deadline outlined in RFP Timeline herein. Daily report and Inspection report formats have been attached as Exhibits D and E. 'C Spire has provided sample copies of the Master Services Agreement - that the Respondent must execute within 10 calendar days after notice of C Spire’s acceptance of a Proposal. The Respondent is responsible for reviewing the Master Services Agreement prior to submitting its Proposal. Except for any exceptions clearly identified in the Respondent's Proposal, the Respondent’s submission of a Proposal and execution of the Proposal Signature Form shall indicate the Respondent’s acceptance of the terms and conditions of the Master Services Agreement
Reporting Requirements |  | All Respondents, and their subcontractors, if any, hereby acknowledge that C Spire, as a recipient of a Federal grant award, is required to report certain information to Federal agencies, inlcuding construction progress and workforce details. As such, each Respondent agrees to provide C Spire with all information requested by C Spire so as to allow C Spire to meet any requirement under a Federal grant award, including, but not limited to, completing and returning the Monthly Subcontractor Report Form and Monthly Workforce Report Form attached to this RFP, for both Respondent and all of its subcontractors, if any. Both the Monthly Subcontractor Report Form and Monthly Workforce Report Form must be completed and emailed to tc-grantsupport@cspire.com in their entirety by the 5th calendar day of each month following the execution of the Master Services Agreement.
Authorized Signature |  | Proposals must contain the signature of the duly authorized officer or agent that is empowered with the right to bind the Respondent. Print, sign, and return the RFP Attachment “E” Proposal Signature Page with the Proposal.
Insurance Requirements |  | A selected Respondent shall purchase and maintain insurance of the following types of coverage and limits of liability as well as and any permit insurance coverages as specifically required: Business Automobile Liability. 1. Business Auto Liability with limits of at least $1,000,000 each accident. 2. Business Auto coverage must include coverage for liability arising out of all owned, leased, hired and non-owned automobiles. 3. C Spire and all other parties required of C Spire shall be included as Insureds on the Automobile Liability policy. Commercial Umbrella with Umbrella limits must be at least $2,000,000 each occurence with Annual Aggregate of not less than $2,000,000 to apply in excess of all insurance coverage's stipulated. Workers Compensation and Employers Liability with limits of Employers Liability Insurance limits of at least $1,000,000 Each Accident, $1,000,000 each employee for Injury by Disease and $1,000,000 Aggregate for Injury by Disease. Professional Liability Insurance. 1. Professional Liability (E&O) with limits of at least $1,000,000 each incident with an Annual Aggregate of not less than $2,000,000. 2. Professional Liability coverage must include coverage for claims arising out of failure to deliver, financial losses, negligence, or construction errors or oversights for service performed under the Construction Services Agreement. Company shall be included as an additional insured on all coverage’s required hereunder, with such coverage’s applying on a primary basis. Certificate holder and additional insured must be shown as and sent to: Troy Cablevision, Inc. d/b/a C Spire and It's Affiliates 1006 South Brundidge St. P O Box 1228 Troy, Alabama 36081-1228
Waiver of Subrogation |  | The Respondent agrees to waive all rights against C Spire and C Spire’s project manager(s), agents, officers, directors and employees, as well as any affiliate or subsidiary of C Spire, including its agents, officers, directors and employees, for recovery of damages to the extent these damages are covered by commercial general liability, professional liability commercial umbrella liability, business auto liability or workers compensation and employers liability insurance maintained per requirements stated above. Any Subcontractor’s Workers Compensation policy will be required to have a “Waiver of Right to Recover from Others” Endorsement with Respondent, C Spire and their project manager(s), agents, officers, directors and employees, as well as any affiliate or subsidiary of C Spire, including its agents, officers, directors and employees. Respondent shall furnish C Spire with a Certificates of Insurance, evidencing that such insurance is provided and is in full force and effect before starting work and, at any other time requested by C Spire. Insurance documents should be submitted with the signed Construction Services Agreement. All of said Certificates shall set forth on the face thereof contractual coverage as required herein. No amendment or cancellation of any of the required policies shall be effective until after 30 calendar days' notice, in writing, to C Spire. The failure of the Respondent to supply Certificates evidencing full compliance with the requirements of the provision shall not abrogate its duty to provide and maintain the required insurance, including, but not limited to, the naming of C Spire as an Additional Insured.
Final Decision/Right to Reject |  | Respondent assumes all costs and risks associated with any submission of a Proposal. C Spire reserves the right, after opening a Proposal or at any other point during this process, to: 1. Reject any or all Proposals. 2. To modify, amend, or cancel this RFP. 3. To modify or postpone the engagement for the Work. 4. Accept one or more Proposals that, in C Spire’s sole discretion, are in the best interest of C Spire. 5. Select no Proposals at all.
Small and Minority Businesses, Women’s Business Enterprises, and Labor Surplus Area Firms |  | Pursuant to 2 CFR § 200.321, Respondent must take all necessary affirmative steps (as described in 2 CFR § 200.321) to assure that minority businesses, women's business enterprises, and labor surplus area firms are used when possible. Respondents are to identify the extent to which Small Businesses ("SBs"), Veteran-Owned Small Businesses ("VOSBs"), Service-Disabled Veteran-Owned Small Businesses ("SDVOSBs"), HUBZONE Small Businesses ("HUBZONE SBs"), Small Disadvantaged Businesses ("SDBs") Woman-Owned Small Businesses ("WOSBs"), Historically Black Colleges/Universities or Minority Institutions ("HBCU/MIs"), Minority-Owned Businesses ("MOBs"), or Local (Alabama) Businesses ("LBs") would be utilized in the performance of the Inspection Services Agreement. For all SBs, as defined by the North American Industry Classification System ("NAICS") code applicable to this RFP, and HBCU/MIs, MOBs or LBs, Respondents' own participation as a SB, VOSB, SDVOSB, HUBZONE SB, SDB, WOSB, HBCU/MI, MOB or LB must be identified in its Proposal, and will be considered in evaluating Respondents’ Qualifications, Expertise and Experience Factors. For the purpose of C Spire’s Disadvantaged Business Enterprise ("DBE") Participation Plan, a small business is defined in accordance with the Small Business Administration’s size regulation 13 CFR § 121.201. In addition, as defined by the NAICS code applicable to this RFP, Respondents' own participation as a SB, VOSB, SDVOSB, HUBZONE SB, SDB, WOSB, HBCU/MI, MOB or LB is to be identified in its Proposal, and its DBE participation will be considered in evaluating the Socioeconomic Considerations, Location, and Value Added Factor. All Respondents are to provide the following: (1) The names of DBEs and SBs, VOSBs, SDVOSBs, HUBZONE SBs, SDBs, WOSBs, HBCU/MIs, MOBs or LBs who would participate in the proposed Inspection Services Agreement, including identification of specific components to be produced or services to be performed by them; (2) The estimated total dollars of such work and percentage of the total estimated proposed services provided by said DBEs and SBs, VOSBs, SDVOSBs, HUBZONE SBs, SDBs, WOSBs, HBCU/MIs, MOBs or LBs; and (3) Copy of small, minority, and local businesses certification from issuing state authority or agency.
General Terms and Conditions |  | Funds Availability. An award resulting from this RFP is automatically canceled if Federal funds under this Project are not appropriated or not otherwise made available to support the Project’s commencement or continuation of performance under a Construction Inspection Services Agreement. Compliance with Laws. Respondent must, in performance of work under a Construction Inspection Services Agreement , fully comply, with all applicable Federal, state, or local laws, rules and regulations, including, but not limited to, the Notice of Funding Opportunity (U.S. Department of Commerce, National Telecommunications Information Administration Notice of Funding Opportunity ("NOFO") No. NTIA-MMG-2-2022, Middle Mile Grant Program, dated May 13, 2022) and all other applicable Executive Orders, public policies, and guidelines governing Federal financial assistance awards and any Federal financial assistance project covered by this Contract (collectively, the “Authority”). Any subletting or subcontracting by Respondent subjects its subcontractors to these compliance requirments. As such, Respondent agrees that it shall comply, and it shall require and ensure that any and all subcontracts and subcontractors shall also comply, with the Authoirty and the terms and conditions described in the Federal Grant Provisions attached hereto and fully incorproated herein by reference thereto. Please find a link to the MMG NOFO here: https://broadbandusa.ntia.doc.gov/sites/default/files/2022-05/MIDDLE%20MILE%20NOFO.pdf.
Costs Borne by Respondent |  | C Spire will not pay for any information requested herein and is not liable for any costs incurred by the Respondent in responding to this RFP.
Ownership Rights and Disclosure of Information |  | All Proposals submitted become the property of C Spire. Proposals will not be returned and may be subject to the requirements of the Freedom of Information Act and/or the Alabama Public Records Act. Pricing and other information that is an integral part of the Proposal cannot be considered confidential. C Spire reserves the right to use any and all concepts presented in any Proposal to obtain the most beneficial and effective path to achieving its desired goals for the Project. Selection or rejection of a Proposal shall not affect this right. All Proposals meeting the criteria of this RFP will be evaluated and, at C Spire’s sole discretion, an award may be made to the Respondent or Respondents who demonstrate the best ability to satisfy the Scope of Work in the timeliest and most cost-effective manner.
Conflict of Interest |  | The Respondent must identify any conflict of interest that may arise from work performed for C Spire. C Spire reserves the right: 1. To disqualify any Respondent or reject any Proposal at any time solely on the grounds that a real or perceived legal or policy conflict of interest is presented; 2. To require the Respondent to take any action or supply information necessary to remove the conflict; or 3. To terminate the Master Services Agreement or any other contract arising from this RFP, if any such relationship would constitute or have potential to create a real or perceived conflict of interest that cannot be resolved to C Spire's satisfaction.
No Gifts and Gratuities Policy |  | C Spire's Code of Ethics policy has a strictly enforced requirement that C Spire and its staff are prohibited from accepting any favors or gratuities from contractors, potential contractors, sub-agreement parties, or from anyone that could potentially be involved in any aspect of C Spire's business.
Formulas:
Action Needed = +[Action Needed, row above]+22
Note on D56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make sure Exhibit and Appendix Reference are correct @ final Reply: Uniform reference to: Master Services Agreement, Material Purchase Agreement, Construction Services Agreement
Note on D60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make sure Exhibit and Appendix Reference are correct @ final

## 2. Questionnaire
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Questionnaire RFP Number: MMG050725_Inspection Services
Corporation
Partnership
Instructions: Please answer the questions below by entering your responses in the fields marked in yellow | [6 empty] | Sole Proprietor
Respondent Questionnaire | [6 empty] | Other
1.1 CONTACT INFORMATION
Item |  | Primary Contact |  |  | Secondary Contact
Name:
Electronic Signature:
Title:
Phone No.:
Cellular Phone No.:
E-Mail:
1.2 COMPANY INFORMATION
Parent / Holding Company
Company Web Address
Company Headquarters Address
Company location from where this project will be managed
Number of Employees
Is the company public or privately held |  |  | Please Select |  | Add any comment here (if required)
Ownership type |  |  | Please Select |  | Add any comment here (if required)
Is your company a diverse owned business. If yes, please also mention if you hold a certificate showing this status. |  |  | Please Select |  | Add any comment here (if required)
1.3 FINANCIAL INFORMATION
|  |  | 2022 |  | 2023 | 2024
1.3.1. Total Revenue
1.3.2. Total Net Profit
1.3.3. Please provide relevant information about any lawsuits, liens, foreclosures, or other legal/financial actions that are pending, in progress, or which have been brought against the company or any of its officers/principals in the past three years.
1.3.4. Are you open to sharing your audited financial statements with C Spire? |  |  | Please Select |  | Add any comment here (if required)
1.3.5. Please specify your coverage for general liability, workers compensation, professional liability, and errors & omissions insurances. C Spire requires a minimum of $1,000,000 in liability insurance.
1.4 COMPLIANCE
1.4.1. Is your company and its subcontractors properly licensed and registered in accordance with Alabama state requirements? The company must be registered and licensed to perform work in the State in which it is being performed prior to the contract being issued. |  |  | Please Select |  | Add any comment here (if required)
1.4.2. Respondent agrees and acknowledges that it and all those with whom it subcontracts, shall, in performance of the Work under a Master Services Agreement , fully comply with all applicable Federal, state, or local laws, rules and regulations, including, but not limited to, the Notice of Funding Opportunity (DOC, NTIA Notice of Funding Opportunity No. NTIA-MMG-2-2022, Middle Mile Grant Program, dated May 13, 2022) (the “NOFO”) and all other applicable Executive Orders, public policies, and guidelines governing Federal financial assistance awards and any Federal financial assistance project covered by this Contract (collectively, the “Authority”). Any subletting or subcontracting by Respondent subjects its subcontractors to these compliance requirements. As such, Respondent must comply, and it shall require and ensure that any and all subcontracts and subcontractors shall also comply, with the Authority and the terms and conditions described in the Federal Grant Provisions attached hereto and fully incorproated herein by reference thereto. Do you comply with the Authority and the terms and conditions described in the Federal Grant Provisions attached hereto, to the extent applicable? Will you require and ensure that any and all of your subcontracts and subcontractors also comply with the Authority and the terms and conditions described in the Federal Grant Provisions attached hereto, to the extent applicable? |  |  | Please Select |  | Add any comment here (if required)
1.4.3. You should have received a 'Master Services Agreement' along with this RFP. Kindly confirm that you have read, understood, and agreed to all requirements, terms, and conditions in this agreement |  |  | Please Select |  | Add any comment here (if required)
1.5 WORK EXPERIENCE AND CLIENTELE
1.5.1. How many years of experience do you have in providing inspection services to telecommunications companies?
1.5.2. Are you currently doing business with C Spire? If so, what percent of your total business is it?
1.5.3. Who are your current major telephone and wireless company clients, if any?
1.6 SCOPE OF INSPECTION SERVICES
1.6.1. Do you certify that you, as well as your contractors and sub contractors, have not been found to have violated laws such as the Occupational Safety and Health Act, the Fair Labor Standards Act, Title VII of the Civil Rights Act of 1964, and relevant safety standards as determined by ADECA including the Safety Code, Alabama state labor and employment, applicable labor and employment laws for the preceding three years |  |  | Please Select | Add any comment here (if required)
1.6.2. What is your typical response time for scheduling an inspection?
1.6.3. What is the typical size of your inspection team ?
1.6.4. How do you manage inspections across multiple sites simultaneously?
1.7. QUALIFICATIONS AND TECHNICAL CAPABILITITES
1.7.1. What certifications and qualifications do your inspectors hold?
1.7.2. How do you ensure ongoing training and upskilling of your inspection team?
1.7.3. What technology and tools do you use for inspections (e.g., drones, GIS mapping, AI-based defect detection)?
1.7.4. What percentage of your inspections are conducted by in-house staff versus third parties? How do you ensure consistency between in-house and subcontracted inspections?
1.7.5. Do you conduct background checks and safety training for your personnel? |  |  | Please Select | Add any comment here (if required)
1.8. DAMAGES & QUALITY ASSURANCE
1.8.1. Do you offer re-inspection services after corrective actions are completed? |  |  | Please Select | Add any comment here (if required)
1.8.2. How do you track and report repeated issues or contractor performance over time?
1.8.3. Do you offer KPIs or dashboards for ongoing quality monitoring?
1.9 REFERENCES
1.9.1. Please provide references to where your firm has provided similar services |  |  | Reference 1 |  | Reference 2 | Reference 3
|  |  | Company Name |  | Company Name | Company Name
|  |  | Company Address |  | Company Address | Company Address
|  |  | Point of Contact Name |  | Point of Contact Name | Point of Contact Name
|  |  | Phone Number |  | Phone Number | Phone Number
|  |  | Email Address |  | Email Address | Email Address
1.10 Respondent ASSURANCE
1.10.1. Respondent must lock the pricing submitted within the 'Pricing Sheet' for the entire lifecycle of the 'Connect Alabama' project. Do you comply with this requirement? |  |  | Please Select |  | Add any comment here (if required)
1.10.2. Payment Schedule Contractor may invoice twice a month. Generally, invoices shall be prepared semi-monthly, ending on the 15th and the last day of the month. Respondent shall submit each invoice for completed work under a specific Project Segment in triplicate. The amount invoiced shall be broken down by each item of work performed. Each invoice shall bear the signature of an authorized representative of Respondent. C SPIRE must approve each invoice submitted to C SPIRE prior to rendering any payment to Respondent under any such invoice. Respondent agrees all amounts payable by C SPIRE for services properly performed in accordance with the Construction Inspection Services Contract and accepted by C SPIRE shall be paid net thirty (30) days from the receipt of an approved invoice by C SPIRE, subject to the terms and conditions of the Construction Inspection Services Agreement. Following the commencement of the work hereunder, Respondent shall comply with the invoicing requirements described below. Additional payment terms are outlined in the Construction Services Agreement, Section 7. |  |  | Please Select |  | Add any comment here (if required)
1.10.3. Respondent must also show C Spire that they have liability insurance, as outlined in Insurance Requirements under worksheet tab "1. Instructions". Insurance should protect against any claims or damages that might arise during the project. Please confirm if you comply with this requirement |  |  | Please Select |  | Add any comment here (if required)
Please Select
WMBE Minority Women Business Enterprise
MBE Minority Business Enterprise
WBE Women Business Enterprise
SDBE Small Disadvantage Business Enterprise
VBE Veteran Business Enterprise
SDV Service-Disabled Veteran
8A Small Disadvantage Business
HUB Historically Underutilized Business

## 3. Construction Details
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Construction Details RFP Number: MMG050725_Inspection Services
Instructions: Below are the details regarding all the Network Construction activities
| Aerial Construction: See Typicals | - In aerial deployments, C Spire would apply for access to attach onto existing poles owned by municipal, county, cooperative and private telecommunications and power companies. - During the engineering process, C Spire would determine the height at which the attachment would be placed. - C Spire at some locations would set its own poles where utility poles are inaccessible and underground construction is not feasible. - Each C Spire pole set would include a #6 bare copper wire beginning at the butt of the pole and ending at the height of the strand. - On all poles a ¼” steel strand would be attached using standard pole line hardware. Fiber will be single lashed to the ¼” strand except at road and railroad crossings, where it will be double lashed. All poles will be grounded to the vertical ground wire and straps and spacers will be placed beside the lashing clamp on each side of each pole. A fiber marker will be placed on fiber at each pole. - Metro/Longhaul Fiber is installed using standard construction processes with expansion loops approximately every 1,000 feet and splice points ranging from approximately 3,000 to 20,000 feet. Distribution Fiber is installed using standard construction processes with no expansion loops added. Tap loops will be placed at every pole as noted on job print and will be two times strand height plus 10 feet. The tap loop will then be rolled up neatly with a circumference of 2 feet and securely mounted to strand.
| Underground Construction: See Typicals | - Underground construction will be the preferred methodology with hand-holes placed no greater than 1,500 feet along the route. This build will have areas where topography, wetlands, constructability, or other unforeseen factors dictate where directional boring will be the only method deployed. - Underground Construction for this Project would be accomplished in four different methods: plowing, directional boring, excavating, and fiber pulls through existing coduit. - Upon issuance of Notice to Proceed, the Respondent is responsible for notifying Alabama 811 (formally Alabama One Call) to have existing underground utilities located. If the Respondent fails to make contact with Alabama 811 and follow the required procedures, all damages to underground utilities will be the responsibility of the Respondent. - Where there is no existing conduit through which fiber can be pulled, Respondent will install new below ground conduit. The process of burying the conduit would be performed by plowing, directional boring or excavating. Upon completion of work, the site would be returned to Pre-Project conditions as soon as possible. • In proposed plow areas, a machine would open the earth to a depth of approximately 36” or applicable depth, install the fiber and close the trench in a single pass. • In proposed directional bore areas (i.e., under roads and railroad tracks), bores would be perpendicular to the resource to minimize bore length. Any bore depth shallower than 36” or deeper than 60” must be preapproved. • In proposed excavated areas, an excavator or back-hoe would open a hole for the purpose of starting a plow, connect bored pipes, set hand holes, or other tasks as they arise. In this case the depth & width should be no larger than required to complete the task at hand. - Fiber will be installed in conduit based on manufacturer recommendations, some installations will only be allowed to jetted in. - Along each fiber run, hand holes and/or pedestals will be installed on an as-needed basis, notably at splice (i.e., fiber connection) and distribution points to the existing backbone and at lateral connections. These provide access to the underground infrastructure for potential lateral connections. Installation would include digging the hole, laying the gravel base and burying the hand hole or pedestal base to existing ground level. Upon completion, the area would be restored to Pre-Project conditions except for standard access lid, cover, or pedestal top. - In proposed excavating, plowing and directional boring locations, Respondent would lay conduit immediately following the ground-disturbing activity and return the site to Pre-Project conditions. Construction at each such location generally should be completed within one (1) day. Fiber markers will then be placed along right of way boundary as noted on construction prints.
| Fiber Splicing: | - A typical splice point would be one closure with multiple fibers ranging from 288 count to 12 count. C Spire will use a loose tube fiber and spiderweb ribbon cable construction. C Spire will be using single fiber fusion splicing as well as 12 fiber ribbon fusion splicing. In some cases, ribbon splicing will be accomplished by using a process called ribbonizing, where a binder of single fibers are put into a ribbon configuration and then an adhesive is applied to keep the fibers in a ribbon pattern for splicing. - C Spire will also install 2, 4 and 8 port fiber taps. These taps will be installed in the distribution cable. A midsheath entry will be made and a single fiber will be broken and spliced to 2 existing .900 micron jumpers inside the tap housing. The remaining 12 fibers will remain as express fibers passing through the tap. - All splices made will have an insertion loss of .02 average (.05 maximum) when using a bidirectional OTDR test at 1550nm and 1310nm. All splices are to have a return loss of 45db or greater. Traces of the bidirectional tests are to be provided to C Spire in digital format immediately following job completion. Traces are to be labeled by the CableID, Binder, Filter and Test Location. C Spire reserves the right to require more stringent loss and reflection standards on any cable deemed necessary.
| Scope of Work: Segments, Standards and Termination | Inspection Services are to include but not limited to, Inspecting OSP fiber construction for quality while ensuring C Spire construction standards are met. All C Spire Safety Practicing are to be adhered to. Daily reporting and documentation is required and submitted daily to the assigned C Spire Supervisor. The following is a list of proposed segment with approximate distances: - Segment A: Fort Davis to Montgomery 105 segment miles - Segment B: Dothan to Phenix City/Midway 133 segment miles - Segment C: Montgomery to Alabaster/Selma 136 segment miles - Segment D: Bay Minette to Elba/Florala 167 segment miles - Segment E: Monroeville to Jackson Eutaw 139 segment miles - Segment F: Ariton 2 segment miles All Respondents will be required to produce detailed daily construction progress reports. All billing will be from approved progress reports. Any Change Orders must be Pre-Approved by a C Spire Project Manager or higher. At C Spire's sole discretion, each segment may be awarded separately or a Respondent may be awarded multiple segments. The construction topology will be buried except where terrain or physical conditions of the cable require aerial.
Water Bodies | Water Bodies | There will be multiple water bodies that will require crossing to complete construction of the fiber cable along the most economical routes. The fiber will cross six (6) water bodies that are maintained by the United States Army Corps of Engineers (USACE) and several other water bodies. The crossings are as listed: (1) Cowikee Creek (USACE waterbody), Hwy. 431, north of Eufaula, AL in Barbour County for a distance of approximately 450 feet; (2) Chewalla Creek in the Walter F. George Reservoir (USACE waterbody), Hwy. 431, north of Eufaula, AL in Barbour County for a distance of approximately 320 feet; (3) Barbour Creek (USACE waterbody), Hwy. 431 near Eufaula, AL in Barbour County for a distance of approximately 388 feet; (4) Cheneyhatchee Creek (USACE waterbody), Hwy. 431 near Eufaula, AL in Barbour County for a distance of approximately 1,500 feet; (5) Lake Martin, Hwy. 280 in Tallapoosa County for a distance of approximately 920 feet; (6) Tallapoosa River, Hwy. 231, northeast of Montgomery in Montgomery County for a distance of approximately 510 feet; (7) R.E. “Bob” Woodruff Lake (USACE waterbody), Hwy. 31, northwest of Montgomery, AL in Autauga County for a distance of approximately 850 feet; (8) Black Warrior River (USACE waterbody), Hwy. 43 north of Demopolis, AL at the Greene and Marengo County line for a distance of approximately 500 feet; (9) Tombigbee River, Hwy. 43 west of Jackson, AL at the Clarke and Washington County line for a distance of approximately 600 feet; (10) Alabama River, Hwy. 84, Claiborne, AL in Monroe County for a distance of approximately 700 feet. There are numerous small ponds, streams, rivers, and lakes along the proposed project route. Portions of the proposed project area contain these features; however, the construction will take place within previously disturbed grassed and paved roadside ROWs. Existing roads, bridges, and stream crossings exist across large‐scale waterways along the project route. All water features identified along the project route will be crossed via directional boring, mounted on existing aerial pole lines, or span across existing bridges. Some areas along the project route ROW may contain potential wetlands, isolated water features, or roadside ditches. All of these areas will be identified before construction begins and all necessary BMPs, which will include erosion control devices, silt fences, hay bales, rock dams, wattles, etc. will be used during all ground disturbing activities that take place adjacent to waterbodies along the proposed fiber route to prevent any sedimentation and siltation. There will be no anticipated significant adverse environmental impacts to the waterbodies or their recreational use during the construction of the proposed project. C Spire will follow all federal, state and local guidelines for permitting and construction activities to ensure there will be negligible impact to the environment along the proposed project route.

## 4. Inspector Guidelines
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Inspector Guidelines RFP Number: MMG050725_Inspection Services
- Below are the guidelines for the Inspectors:
- Network construction inspection guidelines ensure that all infrastructure—such as fiber optics, towers, ducts, and poles—is built to meet design specifications, quality standards, and safety regulations.
- Inspections are conducted at key stages: before construction (to verify readiness), during construction (to monitor workmanship, material use, and compliance), and after completion (to validate as-built documentation and test results). - Inspectors check for correct installation, proper trenching, splicing quality, HSE (Health, Safety and Environmental) adherence, and ensure that deviations are documented and corrected through non-conformance reports (NCRs). - Reports are typically supported by geotagged photos and submitted within set SLAs, helping telecom companies maintain network reliability, safety, and regulatory compliance.
Particulars | Detailed Guidelines
Safety Gear | 1. The On-Site Inspector and all construction personnel must wear approved high visibility safety apparel at all times. 2. No work should be performed without approved safety gear.
Road Signs | 1. Road Signs should be placed according to ALDOT standards in the appropriate spots relative to where job is being performed. A job being performed in a bend in the road or in a place of low visibility will require more signs and the possibility of flagmen than an area that is straight or has easier visibility. 2. No work should be performed without signs.
Flag man | 1. Whenever a directional boring technician is locating across a road, there should always be a flag man provided by the construction company. 2. Flag man should be extra careful to give clear and decisive signals in order to prevent an accident.
Blocking Part of a Road | 1. Our Goal is to always keep the flow of traffic as smooth as possible. 2. Blocking part of a road is discouraged. However, there are a few areas in which we have to do so. Use extreme caution when doing so. 3. All vehicles associated with the construction crew and the on-site inspector should be parked on the same side of the road. This keeps those who are driving through the work site from having to dodge obstacles on both sides of the road. 4. Poorly parked/positioned trucks and equipment can and will cause those in the community to become frustrated as they attempt to drive through the work site. This should be avoided at all times. 5. If trucks and equipment do not allow safe passage by commuters then no construction should take place until the trucks and equipment have been placed in a safe position for commuters to pass by safely. 6. Orange cones should be placed around all parked trucks and equipment. An area with a lot of traffic will require more cones than a rural area. 7. Hazard lights should be visible at all times to all on-coming traffic.
Locates | 1. Locates should be called in by the construction crew a minimum of two days before any construction begins. 2. The On-Site Inspectors should observe the work area and note if utilities have been located. 3. If utilities have not been located, then construction should NOT take place until the utilities are located or permission to proceed is given by the Project Supervisor. 4. The color of the paint will signify what utility is underground at that location. a. Gas – yellow b. Water – blue c. Power – red d. Communication – orange e. Sewer - green
Bore Pits | 1. All excavation must comply with OSHA at all times. 2. No personnel is allowed in a pit 4’ or deeper unless it has been properly sloped and/or shored to meet OSHA specifications to ensure the safety of all construction personnel. 3. All bore pits should be coned off or fenced off with a safety net. 4. Bore pits that are not covered should be backfilled before the construction crew leaves the work site for the night. 5. If construction crew leaves an open/uncovered bore pit on their way from the job site, the On-Site Inspector should call and ask the construction crew to return immediately and close all bore pits properly. If they refuse then notify your Project Supervisor immediately.
Attitude- Towards Construction Crew | 1. WORKING TOGETHER- Although you are the company representative on the job site whenever the Project Supervisor is not there, we DO NOT condone the act of tyranny/rudeness. Common courtesy should be shown to all personnel. 2. RESPECT- It is your responsibility as an On-Site Inspector to help create a nice friendly and safe working environment. There’s an old saying “you reap what you sow”. If you are kind to your crew they will return the favor. 3. CALL- If you ever encounter an extremely rare situation of a construction crew being disrespectful to you, walk away and contact your Project Supervisor immediately.
Attitude- Towards Community | 1. CURIOUS- Most people in the community that you are working in simply want to know what you are doing. It is ok to explain what the construction crew is about to do. However, you should NEVER tell a curious resident that we are bringing them 4G, fiber to the home or promise them faster cell phone service. If they are interested in our products please have them contact your Project Supervisor and he will direct them to the right C Spire personnel. 2. COURTESY- You are expected to always treat those in the community with the utmost respect and kindness. Regardless of their tone and demeanor to you, you are expected to be kind and polite to them at all times.
Attitude- Towards Upset Property Owner | In the event you should come across a property owner who is upset because he/she believes that you are on their property. 1. Always esteem the property owner as a friend. We are not here to make enemies. 2. Retrieve your permits and construction drawing and try to explain to them that you are on the right of way. 3. If the Property Owner still insists that you are on his/her property, then stop all construction and contact your Project Supervisor immediately. 4. Your responses of “yes sir” and “yes ma’am” in a polite tone will help us to resolve the issue much sooner.
Appearance | 1. CLEAN CLOTHES- We expect you to start every work day with clean clothes. 2. PERSONAL HYGIENE- We expect all of our On-Site Inspectors to shower and to pay attention to personal hygiene on a daily basis.
Available On Site | 1. No construction should begin without the On-Site Inspector being present. 2. The On-Site Inspector should communicate with construction foreman in order to coordinate arrival time for each day. 3. The On-Site Inspector is expected to be on site during construction unless relieved or special arrangements have been made. 4. It’s impossible to document what you’re not on site to see.
Accuracy | 1. The On-Site Inspector should have a very high interest in being accurate with his documentation. 2. If an On-Site Inspector is using a GPS unit, he should be sure to check the accuracy indicator on his unit to be sure that he is receiving an accurate position. 3. If an On-Site Inspector is not using a GPS unit, he should use a measuring wheel or tape measure. He should be sure to document if his measurements are from edge of pavement, back of curb, white line or center line of road.
As-built | 1. The as-built should reflect exactly what happened out in the field as the construction was taking place. It is very important that the On-Site Inspector doesn’t disregard any changes that were made in the field that differs from the construction drawings. 2. The as-built should be legible, neat and done as professionally as possible. 3. The as-built should be kept clean of dust, dirt and mud. 4. The as-built should show a depth for every 30’ of bored footage installed. 5. The as-built should show the correct location of a hand hole that was moved from original location on construction drawings. 6. The On-Site Inspector should be sure to have his as-built finished at the conclusion of the job. 7. The On-Site Inspector should give the finished as-built to the appropriate person ASAP. This will keep the as-built from being misplaced, damaged or completely lost.
Clean-up | 1. A job is not finished until it is clean! It’s imperative that we maintain a friendly working relationship with each city we do construction in. 2. Concerning bigger jobs, it is the On-Site Inspector’s responsibility to be sure that the construction crew is cleaning as they go. Whenever there are multiple areas on a bigger job needing attention, the On-Site Inspector should confer with his Project Supervisor about shutting down the boring rigs. The Project Supervisor will give the On-Site Inspector the yes or no to shut down boring rigs in order to clean up job. 3. It is the On-Site Inspector’s responsibility to be sure that the construction crew cleans up and repairs every area that’s been damaged by their equipment. 4. It is the On-Site Inspector’s responsibility to make sure that the construction crew is not installing marker poles covered with mud. 5. The On-Site Inspector should be aware and not allow construction workers to leave coffee cups, coke bottles and snack wrappers scattered along the work site. Also NO trash is to be placed in any excavation!
ALDOT Right of Way | 1. ALDOT has the authority to shut down construction if the job site is not operating according to their rules. The On-Site Inspector should make sure that all of ALDOT requirements are fulfilled in order to avoid interruption of construction. 2. All safety gear is a MUST. The On-Site Inspector’s responsibility is to make sure that the construction crew is wearing the proper safety gear. 3. Permits are a MUST in order to begin working on ALDOT right of way. The On-Site Inspector should be sure that he and the construction crew understand what the permits are permitting us to do. 4. Road signs are a MUST. A sign should be placed on both sides of the road at approximately 1500’, 1000’ and 500’ (refer to ALDOT requirements) before you get to where the workers are located. 5. The On-Site Inspector must refer to the ALDOT permit when working on ALDOT right of way. As far as ALDOT is concerned, our construction drawings are useless when we are working on ALDOT right of way. 6. The On-Site Inspector should verify that the running line was flagged correctly per the permit. Typically the running line will be in the back 5’ of the right of way and that cannot be changed without permission of ALDOT… Example, if the right of way on a ALDOT highway is 50’ from the center line of the road, then the construction crew is only allowed to bore (45ft- 50ft) from the center line of the road. The On-Site Inspector should always be aware of all right of ways changes because there could be many changes in a one mile stretch of road. 7. No changes are allowed on ALDOT right of way without the approval of ALDOT. If the construction crew and/or the On-Site Inspector runs into an unforeseen problem, the On-Site Inspector should contact the Project Supervisor (even if the construction foreman says he did) and the Project Supervisor will instruct the On-Site Inspector going forward. 8. The On-Site Inspector should be sure that all bore pits are backfilled before the crew leaves the work site. No bore pit should be left open more than 10 hours in a day. 9. If the construction crew leaves the work site before handling all of their requirements, the On-Site Inspector should call the construction foreman and ask him to return and properly shut down the work site. If construction crew doesn’t return immediately, the On-Site Inspector should immediately inform his Project Supervisor.
Railroad Right of Way | 1. When on railroad right of way, some of the railroad companies will send a railroad inspector. The railroad inspector is the higher authority whenever he is present. The On-Site Inspector and construction crew must abide by the railroad inspector’s instruction. 2. Some railroad Inspectors will have an orientation with the On-Site Inspector and the construction crew. 3. The On-Site Inspector and construction crew will be asked to wear the following personal protection equipment (PPE). a. Hard Hat b. Steel toe boots c. Reflective high visibility safety vest d. Blue Jeans e. No shorts will be allowed 4. Typically the construction crew will be asked to place a marker pole on each side of the railroad tracks. 5. In some instances the railroad inspector will ask that no one cross the train tracks without him being present and gives you permission to cross.
Damaged Utility | 1. Although our construction crews take extreme caution to not disturb existing underground utilities, an accident will happen from time to time. Whenever an underground utility is damaged by one of the construction crews, the On-Site Inspector should immediately begin to document the event by filling out a damage report. The construction foreman should immediately call the owner of whatever utility is damaged. 2. PICTURES- a. The On-Site Inspector should immediately begin to take pictures of the damaged area. b. The On-Site Inspector should get pictures of the locate markings and in the same picture include the damaged area. Several pictures from different angles is encouraged. c. A damaged water line has the potential to cause a flood and cover any locate markings. Please move quickly. 3. DAMAGE REPORT- a. The On-Site Inspector should always have physical copies of damaged utility reports on the job site along with a damage hit kit. b. The On-Site Inspector should document date, time, city, county, what kind of right of way, what was damaged, who damaged it, time of repair. (See damage report for full list). c. The On-Site Inspector should call his Project Supervisor immediately after he has gathered enough information to fill out a damaged utility report. d. The On-Site Inspector should remember that he is there to report what happened exactly as it happened. Falsifying any report will bring the On-Site Inspector under the intense scrutiny of his Project Supervisor and will bring the On-Site Inspector’s ability to perform the job accurately into question and might lead to more undesirable actions.
Handhole Installation | 1. POSITION OF HAND HOLE: a. PARRALLEL WITH ROAD – The On-Site Inspector should be sure that hand hole is installed perfectly parallel with the road. Crooked hand holes will be frowned upon and the Project Supervisor will ask for the hand hole to be re-installed properly. b. LAY OF THE LAND – The On-Site Inspector should be sure that hand holes are installed at the same angle/slope of the ground. c. FLUSH WITH GROUND - The On-Site Inspector should be sure that the hand hole is installed flush with the ground. d. NOT IN A DITCH – The On-Site Inspector should be aware of hand hole locations and avoid installing a hand hole in ditch or low lying area that collects water. 2. HOW TO INSTALL HAND HOLE: a. TOP OF GRAVEL – The On-Site Inspector should be sure that the hand hole is installed on top of a minimum of six inches of washed rock. A minimum of six inches of rock should be on every side of the hand hole. b. MARKER POLE – The marker pole should be placed in the center of the hand hole. A “J-pipe” should be installed in every hand hole even if it is not a test station. c. GROUND ROD – If the hand hole calls for a ground rod, it should be installed six inches away from the centered marker pole. The ground rod should be installed six inches below the ground. Be careful that the crew doesn’t install ground rod into an existing utility. d. BOLTS IN HH – The On-Site Inspector should check that the construction crew installed the bolts at the completion of the installation.
Marker Pole Installation | 1. TWO FEET DEEP – The 6’ marker pole should be installed 24” deep. The installed height should be four feet (48”). 2. PIN IN – The On-Site Inspector should be sure that the construction crew installs the pin in the pre-drilled holes in the marker pole. 3. LEVEL – The On-Site Inspector should be sure that every marker pole is level/straight. The Project Supervisor will ask for crooked marker poles to be re-installed. 4. CLEAN – The On-Site Inspector should be sure that the new marker pole looks new after installation. The construction crew should remove any mud or debris and clean the marker pole after installation. 5. TEST STATION – If marker pole is located at a hand hole that calls for a test station, the On-Site Inspector should be sure that the construction crew removes pin from orange cap and that test wires are accessible at the top of the marker pole. (See above illustration)
UH-1 at Building Entry | Notice the placement of the ground rod in below illustration
How to field a bore | 1. BEFORE BORE BEGINS: Pre-bore inspection is key for the On-Site Inspector to be effective in the field. Properly starting a bore will increase accuracy and assurance that the bore will pass audit. This is the best time to find errors and make the necessary adjustments to ensure accuracy. a. VERIFY STAKING OF RUNNING LINE – The On-Site Inspector should verify that the running line has been staked and that the contractor is set up to follow that running line. b. TWO FEET OF FLAGS – The On-Site Inspector should keep the construction crew within 2 feet of flags. (This is very important concerning future builds.) c. PROPERTY LINES- i. FRONT OF HOUSE – The On-Site Inspector should discourage the boring crew from excavating directly in front of someone’s home. ii. PROPERTY LINES – The On-Site Inspector should encourage the construction crew to move proposed bore pit to a property line. 2. SHOOT INTO A BORE PIT – Every bore should begin with the boring crew shooting into a bore pit at the beginning and the ending of a bore. Any deviation needs to be approved by your Project Supervisor. 3. DEPTHS EVERY THIRTY FEET – The On-Site Inspector should record the depth of the bore every 30 feet beginning at the point where the bore reaches forty inches and to where the bore ends at forty inches. a. BORE DEPTH: C Spire fiber’s policy is that every bore should be executed at a depth between thirty-six inches and eight feet. If a particular area has existing utilities that requires the bore to go deeper than eight feet, the On-Site Inspector should do the following: i. Make sure the boring crew returns the bore to between forty inches and eight feet as soon as possible. ii. The On-Site Inspector should document on the as-built why the construction crew exceeded the eight foot depth limit. b. USE STATION NUMBERS FOR ACCURACY – The On-Site Inspector should not rely on his measuring wheel for every 30 feet. The On-Site Inspector should use the station numbers on the drawings to determine where to record the depth every 30 feet… Example - where the bore begins and reaches depth (4’) that should be where the station number begins. Let’s say that the station number there is (1+00). Instead of the inspector rolling his measuring wheel 30’ to record his next depth, the On-Site Inspector should find something on the construction drawing and measure forward or backward to find the accurate location of his next depth. Seeing that our bore began at (1+00) our next recorded depth should be at (1+30). Let’s say that there is a power pole at (1+37) then the On-Site Inspector should go to that power pole and measure back seven feet to (1+30) and record his depth there. c. BORE WILL BE AUDITED – After every job is complete, C Spire fiber will send out auditors to assure that fiber is placed according to C Spire fiber guidelines. Whenever a C Spire fiber auditor comes out to the field and check depths, they will use the method in the above example. If they want to check the depth at (1+30) they will find the power pole at (1+37) and measure back seven feet and locate the fiber in that location.
Reporting Daily Footage | 1. On a daily basis the construction crew will be paid the footage as it appears on the construction drawings unless a major bust is found in the measurements… Example, on sheet one the stations run from 0+00 to 13+10 and the construction crew begins a bore in the middle of the drawing. The On-Site Inspector should assign a station reading to the beginning (6+10) and end (11+20) of the bore and use those numbers (510 feet) to report footages on a daily basis. a. The On-Site inspector should pick out a pole, fire hydrant or meter box with a station assigned and measure to the start of the bore to assign a station number. Doing it this way eliminates arguments over the length of the bore (wheeled, taped, or number of drill rods). b. By using the above method, it covers the On-Site Inspector in the event someone goes on site and checks a depth. The auditor will try to locate a place to check depth and the inspector wants to make sure the auditor checks the depth in the same location he checked or reported a depth. c. The Project Supervisor will correct any discrepancies when the fiber is placed. d. A daily report should consist of the following: Date, footage with station numbers, footage category (Urban, Suburban or Rural), (number of hand holes, ground rods, test stations, marker poles), footage of fiber install, what type of fiber installed (12ct, 24ct, 48ct, 144ct, 288ct) and number of DTS’ are some of the things the On-site Inspector will include in a daily report that is submitted in the Fulcrum Reporting App. 2. EMAIL OR TEXT- The On-Site Inspector will find it to his advantage to store all of his reports electronically but this is not required. The Project Supervisor and the On-Site Inspection will work out the best method to report the daily results. 3. PHONE CALL – a. A Project Supervisor might want you to call him and give him your daily report. b. The Project Supervisor who prefers a phone call will inform the On-Site Inspector of the best time to call him with the report.
Cement/Asphalt Cut & Restore | 1. The On-Site Inspector should measure cement/asphalt removal in square feet. (Length X width= square feet) 2. The On-Site Inspector should NOT report the square footage until the restoration is complete. The contractor will be paid for the section removed and not deducted for the HH lid… Example, if the construction crew cut out a section 4’X5’ we pay 20 square feet even through the lid covers part of the restoration.
SOD Installation | 1. The On-Site Inspector should measure and report any approved SOD installation. 2. The On-Site Inspector should report SOD installation in square yards. [(Length X width = square feet) divided by 9 = square yards] Example: If you measure the area of installation 12’ long and 6’ wide. [(12X6=72sq ft) (72/9= 8 square yards)]
On-Site Inspector Compensation | 1. FULL DAY – Whenever the On-Site Inspector works more than 5 hours, he will be paid for a full day. 2. HALF DAY - Whenever the On-Site Inspector works less than 5 hours, he will be paid for a half day. 3. RAIN DAY- a. If it should begin to rain after 12:00pm, then the On-Site Inspector will be paid for a full day. (The construction crew will be charged a full day against their deadline.) b. If it should begin to rain before 12:00pm after the On-Site Inspector and construction crew have begun to work and the rain causes all work to come to a halt for the entire day, then the On-Site Inspector will be paid half a day. (The construction crew will not be charged for that day. It will be reported as a delay day.)
Fiber Installation | It is extremely important that the On-Site Inspector and construction foreman observe the construction drawings carefully regarding fiber installation. Installing the wrong fiber whenever everything is clearly laid out on the construction drawings will be frowned upon by your Project Supervisor. The On-Site Inspector should never assume that the construction foreman is always right. C Spire fiber is investing in an On-Site Inspector to help prevent overlooks and mistakes. Fiber is very expensive and should be treated valuably by the construction crew. 1. UNDERSTAND - The On-Site Inspector should study the construction drawings until he comes to an understanding of which fiber goes where. Most jobs will use several different sizes of fiber within its fiber route. 2. INVESTIGATE REEL – It is crucial that the On-Site Inspector investigate the fiber reel before the fiber crew begins to install. The On-Site Inspector should note if the numbers on the reel is counting up or down. a. When several reels are used during a bigger install the reels will typically be given a letter and a number (A-74) for identification. b. Great amount of time goes into the calculation of fiber usage during fiber installation. Therefore, the On-Site Inspector should NEVER use a fiber reel in a location that it was not meant for. The On-Site Inspector should contact his Project Supervisor if he comes to a situation in which he believes there is a discrepancy or an error with the fiber. 3. INSTALLATION – a. The On-Site Inspector should monitor the fiber installation. The On-Site Inspector should watch that the fiber is not stretched or bent in a way that will cause harm to the fiber. The On-Site Inspector should be careful to watch for kinks. If a kink in the fiber happens, Installation should be immediately paused and fiber should be inspected for damage. b. OVERNIGHT ON GROUND – The On-Site Inspector should be sure to inform the fiber crew that it is against company policy to leave uninstalled fiber laying on the ground overnight. If equipment failure should happen during install in the evening, the On-Site Inspector should contact his Project Supervisor for instructions on how to proceed. 4. FIBER NUMBERS – a. The On-Site Inspector should record the fiber numbers coming in and going out at every hand hole. Whenever the fiber crew is finished at each hand hole, the On-Site Inspector should ask to see the numbers on the fiber coming in and going out of the hand hole. b. The On-Site Inspector should subtract the numbers to be sure that he has the requested amount of slack that’s on the construction drawings. c. Whenever the fiber crew has successfully installed fiber in two consecutive hand holes, the On-Site Inspector should subtract the number coming out of the first hand hole with the number going into the second hand hole. The difference of these two fiber numbers should be very close to the difference of the two hand holes’ station numbers on the construction drawings. If the difference of the fiber numbers and the station numbers are not even close, then an error has been made. The error should be reported to the Project Supervisor on the next daily report. 5. BOLTS – a. The On-Site Inspector should inform the fiber crew to be sure to replace the bolts in the hand hole after they complete fiber installation in that hand hole. b. The On-Site Inspector should check behind the fiber crew to be sure that the crew is putting the bolts back in the hand holes.
DTS Installation | 1. H-FRAME OUTSIDE OF FENCE: a. MARKER POLE A MINIMUM OF 6’ FROM H-FRAME – Whenever construction drawing calls for a DTS, On-Site Inspector should be sure that marker pole is installed a minimum of 6’ from H-frame. Location of marker pole doesn’t matter, as long as it’s a minimum of 6’ away from H-frame. b. STRIP BACK WIRE – Once the 12ct reaches the “tee” installed at bottom of marker pole, the locate/ground wire should be stripped back and run up the marker pole and should be accessible at the top of marker pole. (See below illustration) 2. H-FRAME INSIDE OF FENCE: a. HAND HOLE OUTSIDE OF FENCE - The construction crew should install a hand hole and water box according to the construction drawings.
Inspector Tips | 1. Take time stamped pictures before and after, see additional guidance outlined on Tab 5. Photo Guidelines. 2. Add totals as you go. 3. Keep a running weekly total of footages. 4. Redline as you go. 5. Buy a smart phone! 6. Use a separate set of drawings for redlines. 7. Work ahead and not from behind. 8. Ask politely. 9. Respect everyone. 10. Communicate with job foreman frequently. 11. Call your Project Supervisor any time you are not sure about something.
Note on D41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Review notation Reply: “Damage Hit Kit”, what is this and is there a form? @ Jerry
Note on D49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Review bore depth notation
Note on D51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Review notation Reply: May need to include screen shots of application for training purposes.
Note on D63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Validate Tab reference/name

## 5. Photo Guidelines
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Photo Guidelines RFP Number: MMG050725_Inspection Services
- Digital Inspection Management (DIM) is an automated quality of work inspection technique utilized by C Spire project managers to ensure that construction standards and quality are achieved. - Below are the guidelines for photo submission - Below are some photo guidelines for your reference
Particulars | Detailed Guidelines
Overview | - Most important guideline is that all submitted photos must be time stamped with: 1) Date 2) Time stamped 3) Address and/or Geo Location 4) Station Number (Bore, HH, test lead, ground rod etc.) - Photos should be clear and specific to the task completed. Focus in on the item illustrated to confirm the quality of work. - Every work area MUST have photos of excavation site before and after the leveling of ground and installation of sod, straw and seed. - Each HH installed will be photographed and verified with an approved measuring device from the EOP, Back of curb or as stated on the drawings.
Pre-Work Photos | - Pre-work photos are essential to confirm quality of work. These photos can determine the condition of the worksite prior to placement of the duct and HHs. Below are the examples:
Post-Work Photos | - Post work photos will confirm the completion of work. It is highly recommended that all invoiced items be displayed to verify that C Spire Standards are achieved. Below are the examples:
Handholes | - Examples for: i. Photo confirmation of Completed shot into Open Bore Pit or HH pit with Gravel bed ii. Overhead view of Handhole with all components installed (duct, cable, ground rod, etc.) iii. Confirmation of installed HHs measured from EOP, back of curb or nearest tie down point as shown on print. Iv. Photo of fully restored work area Including Station number for reference
Cable/Mule Tape Installation | - Examples for: i. Photo of FOC sequential numbers at both end of span placed ii. Provide Photo confirmation of Mule tape placement
Bores | Provide photos of the active worksite with Station numbers included on the time stamp
Cabinets | Provide Photo Confirmation of cabinet installation completed
Completed Work site | Provide photos to confirm each completed worksite
ONT Budi-box
Production Redlines | Must Provide photos of daily production redlines, and a complete set once construction concludes

## 6. Pricing Sheet
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Pricing Sheet RFP Number: MMG050725_Inspection Services
- Please provide your inputs within cells highlighted in green. - This request does not guarantee any award or sole source. C Spire will make award decisions based on a thorough review of all proposals, including all financials, lead times, technical capabilities and service capacities - Other forms of submission will not be accepted nor will submissions submitted directly, to individual staff members
Please note that no additional rounds of negotiations will take place. Kindly ensure that you submit your best and final pricing offer below.
Counties where construction to be carried out | Autauga, Baldwin, Barbour, Bullock, Chambers, Chilton, Choctaw, Clarke, Coffee, Conecuh, Coosa, Covington, Dallas, Elmore, Escambia, Greene, Hale, Henry, Houston, Lee, Macon, Marengo, Monroe, Montgomery, Perry, Russell, Shelby, Tallapoosa, Washington, and Wilcox Counties.
Particulars |  | UOM | Day Rate ($)
Inspector Day Rate |  | Per Day

## 7. Vendor Registration
Troy Cablevision, Inc., dba C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Network Construction Inspection RFP, Pricing Sheet RFP Number: MMG041025_OSP Construction Inspection

## 8. Grant Provisions
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Grant Provisions RFP Number: MMG050725_Inspection Services
EXHIBIT "O"
FEDERAL GRANT PROVISIONS
I. COMPLIANCE PROVISIONS | Respondent Compliance Assurance
A. Equal Employment Opportunity. During the performance of this Agreement, Respondent agrees as follows: 1. Respondent will not discriminate against any employee or applicant for employment because of race, color, religion, sex, sexual orientation, gender identity, or national origin. Respondent will take affirmative action to ensure that applicants are employed, and that employees are treated during employment without regard to their race, color, religion, sex, sexual orientation, gender identity, or national origin. Such action shall include, but not be limited to the following: employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship. Respondent agrees to post in conspicuous places, available to employees and applicants for employment, notices to be provided setting forth the provisions of this nondiscrimination clause. 2. Respondent will, in all solicitations or advertisements for employees placed by or on behalf of Respondent, state that all qualified applicants will receive consideration for employment without regard to race, color, religion, sex, sexual orientation, gender identity, or national origin. 3. Respondent will not discharge or in any other manner discriminate against any employee or applicant for employment because such employee or applicant has inquired about, discussed, or disclosed the compensation of the employee or applicant or another employee or applicant. This provision shall not apply to instances in which an employee who has access to the compensation information of other employees or applicants as a part of such employee’s essential job functions discloses the compensation of such other employees or applicants to individuals who do not otherwise have access to such information, unless such disclosure is in response to a formal complaint or charge, in furtherance of an investigation, proceeding, hearing, or action, including an investigation conducted by the employer, or is consistent with Respondent’s legal duty to furnish information. 4. Respondent will send to each labor union or representative of workers with which it has a collective bargaining agreement or other contract or understanding, a notice to be provided advising the said labor union or workers’ representatives of Respondent’s commitments under this section and shall post copies of the notice in conspicuous places available to employees and applicants for employment. 5. Respondent will comply with all provisions of Executive Order 11246 of September 24, 1965, and of the rules, regulations, and relevant orders of the Secretary of Labor. 6. Respondent will furnish all information and reports required by Executive Order 11246 of September 24, 1965, and by rules, regulations, and orders of the Secretary of Labor, or pursuant thereto, and will permit access to its books, records, and accounts by the administering agency and the Secretary of Labor for purposes of investigation to ascertain compliance with such rules, regulations, and orders. 7. In the event of Respondent’s noncompliance with the nondiscrimination clauses of this Agreement or with any of the said rules, regulations, or orders, this Agreement may be canceled, terminated, or suspended in whole or in part and Respondent may be declared ineligible for further government contracts or Federally assisted construction contracts in accordance with procedures authorized in Executive Order 11246 of September 24, 1965, and such other sanctions may be imposed and remedies invoked as provided in Executive Order 11246 of September 24, 1965, or by rule, regulation, or order of the Secretary of Labor, or as otherwise provided by law. 8. Respondent will include the portion of the sentence immediately preceding Paragraph (1) and the provisions of Paragraphs (1) through (8) in every subcontract or purchase order unless exempted by rules, regulations, or orders of the Secretary of Labor issued pursuant to Section 204 of Executive Order 11246 of September 24, 1965, so that such provisions will be binding upon each subcontractor or Respondent. Respondent will take such action with respect to any subcontract or purchase order as the administering agency may direct as a means of enforcing such provisions, including sanctions for noncompliance: Provided, however, that in the event Respondent becomes involved in, or is threatened with, litigation with a subcontractor or Respondent as a result of such direction by the administering agency, Respondent may request the United States to enter into such litigation to protect the interests of the United States. Respondent further agrees that it will be bound by the above equal opportunity clause with respect to its own employment practices when it participates in Federally assisted construction work: Provided, that if Respondent is a State or local government, the above equal opportunity clause is not applicable to any agency, instrumentality or subdivision of such government which does not participate in work on or under this Agreement. Respondent agrees that it will assist and cooperate actively with the administering agency and the Secretary of Labor in obtaining the compliance of contractors and subcontractors with the equal opportunity clause and the rules, regulations, and relevant orders of the Secretary of Labor, that it will furnish the administering agency and the Secretary of Labor such information as they may require for the supervision of such compliance, and that it will otherwise assist the administering agency in the discharge of the agency’s primary responsibility for securing compliance. Respondent further agrees that it will refrain from entering into any contract or contract modification subject to Executive Order 11246 of September 24, 1965, with a contractor debarred from, or who has not demonstrated eligibility for, government contracts and Federally assisted construction contracts pursuant to the Executive Order and will carry out such sanctions and penalties for violation of the equal opportunity clause as may be imposed upon contractors and subcontractors by the administering agency or the Secretary of Labor pursuant to Part II, Subpart D of the Executive Order. In addition, Respondent agrees that if it fails or refuses to comply with these undertakings, the administering agency may take any or all of the following actions: cancel, terminate, or suspend in whole or in part this grant (contract, loan, insurance, guarantee); refrain from extending any further assistance to Respondent under the program with respect to which the failure or refund occurred until satisfactory assurance of future compliance has been received from Respondent; and refer the case to the Department of Justice for appropriate legal proceedings. | Please Select | Add any comment here (if required)
B. Contract Work Hours and Safety Standards Act. 1. Overtime requirements. No contractor or subcontractor contracting for any part of the contract work which may require or involve the employment of laborers or mechanics shall require or permit any such laborer or mechanic in any workweek in which he or she is employed on such work to work in excess of forty (40) hours in such workweek unless such laborer or mechanic receives compensation at a rate not less than one and one-half times the basic rate of pay for all hours worked in excess of forty (40) hours in such workweek. 2. Violation; liability for unpaid wages; liquidated damages. In the event of any violation of the clause set forth in Paragraph (1) the contractor and any subcontractor responsible therefore shall be liable for the unpaid wages and interest from the date of the underpayment. In addition, such contractor and subcontractor shall be liable to the United States (in the case of work done under contract for the District of Columbia or a territory, to such District or to such territory), for liquidated damages. Such liquidated damages shall be computed with respect to each individual laborer or mechanic, including watchpersons and guards, employed in violation of the clause set forth in Paragraph (1), in the sum of $32 for each calendar day on which such individual was required or permitted to work in excess of the standard workweek of forty (40) hours without payment of the overtime wages required by Paragraph (1). 3. Withholding for unpaid wages and liquidated damages – i. Withholding process. C SPIRE may, upon its own action, or must, upon written request of an authorized representative of the Department of Labor, withhold or cause to be withheld from the contractor so much of the accrued payments or advances as may be considered necessary to satisfy the liabilities of the prime contractor or any subcontractor for any unpaid wages; monetary relief, including interest; and liquidated damages required by the clauses set forth in this Section of the Agreement, any other Federal contract with the same prime contractor, or any other Federally assisted contract subject to the Contract Work Hours and Safety Standards Act (“CWHSSA”) that is held by the same prime contractor (as defined in 29 C.F.R. § 5.2). The necessary funds may be withheld from the contractor under this Agreement, any other Federal contract with the same prime contractor, or any other Federally assisted contract that is subject to the CWHSSA and is held by the same prime contractor, regardless of whether the other contract was awarded or assisted by the same agency, and such funds may be used to satisfy the contractor liability for which the funds were withheld. ii. Priority to withheld funds. The Department has priority to funds withheld or to be withheld in accordance with 29 C.F.R. § 5.2(a)(2)(1) or (b)(3)(i), or both, over claims to those funds by: A. A contractor’s surety(ies), including without limitation performance bond sureties and payment bond sureties; B. A contracting agency for its reprocurement costs; C. A trustee(s) (either a court-appointed trustee or a U.S. trustee, or both) in bankruptcy of a contractor, or a contractor's bankruptcy estate; D. A contractor’s assignee(s); E. A contractor’s successor(s); or F. A claim asserted under the Prompt Payment Act, 31 U.S.C. §§ 3901-3907 4. Subcontracts. The contractor or subcontractor must insert in any subcontracts the clauses set forth in Paragraphs (1) through (5) of this Section and a clause requiring the subcontractors to include these clauses in any lower tier subcontracts. The prime contractor is responsible for compliance by any subcontractor or lower tier subcontractor with the clauses set forth in Paragraphs (1) through (5). In the event of any violations of these clauses, the prime contractor and any subcontractor(s) responsible will be liable for any unpaid wages and monetary relief, including interest from the date of the underpayment or loss, due to any workers of lower-tier subcontractors, and associated liquidated damages and may be subject to debarment, as appropriate. 5. Anti-retaliation. It is unlawful for any person to discharge, demote, intimidate, threaten, restrain, coerce, blacklist, harass, or in any other manner discriminate against, or to cause any person to discharge, demote, intimidate, threaten, restrain, coerce, blacklist, harass, or in any other manner discriminate against, any worker or job applicant for: i. Notifying any contractor of any conduct which the worker reasonably believes constitutes a violation of the CWHSSA or its implementing regulations in this part; ii. Filing any complaint, initiating or causing to be initiated any proceeding, or otherwise asserting or seeking to assert on behalf of themselves or others any right or protection under CWHSSA or this part; iii. Cooperating in any investigation or other compliance action, or testifying in any proceeding under CWHSSA or this part; or iv. Informing any other person about their rights under CWHSSA or this part. In addition, the contractor or subcontractor must maintain regular payrolls and other basic records during the course of the work and must preserve them for a period of three (3) years after all the work on the prime contract is completed for all laborers and mechanics, including guards and watchpersons, working on the contract. Such records must contain the name; last known address, telephone number, and email address; and social security number of each such worker; each worker’s correct classification(s) of work actually performed; hourly rates of wages paid; daily and weekly number of hours actually worked; deductions made; and actual wages paid. Further, the records to be maintained under this Section must be made available by the contractor or subcontractor for inspection, copying, or transcription by authorized representatives of the DOC, NTIA, and the Department of Labor, and the contractor or subcontractor will permit such representatives to interview workers during working hours on the job. | Please Select | Add any comment here (if required)
C. Davis-Bacon Act. Respondent, and its subcontractors, if any, shall comply with the Davis-Bacon Act, as amended (40 U.S.C. §§ 3141-3148), and supplemented by Department of Labor regulations (29 C.F.R. Part 5, “Labor Standards Provisions Applicable to Contracts Covering Federally Financed and Assisted Construction”). In accordance with the statute, contractors must be required to pay wages to laborers and mechanics at a rate not less than the prevailing wages specified in a wage determination made by the Secretary of Labor. In addition, Respondent acknowledges, and will require any subcontractors to acknowledge, that it has reviewed the applicable prevailing wages specified in a wage determination made by the Secretary of Labor and accepts said wage determination. | Please Select | Add any comment here (if required)
D. Clean Air Act and Federal Water Pollution Control Act. “Clean Air Act” 1. Respondent, and its subcontractors, if any, agree to comply with all applicable standards, orders or regulations issued pursuant to the Clean Air Act (42 U.S.C. §§ 7401, et seq.), as amended, including Executive Order 11738 (38 FR 25161). 2. Respondent, and its subcontractors, if any, agree to report each violation to C SPIRE and understands and agrees that C SPIRE will, in turn, report each violation as required to assure notification to NTIA and DOC, and the appropriate Environmental Protection Agency (“EPA”) Regional Office. “Federal Water Pollution Control Act” 1. Respondent, and its subcontractors, if any, agree to comply with all applicable standards, orders, or regulations issued pursuant to the Federal Water Pollution Control Act (33 U.S.C. §§ 1251, et seq.), as amended, including Executive Order 11738 (38 FR 25161). 2. Respondent, and its subcontractors, if any, agree to report each violation to C SPIRE and understands and agrees that the C SPIRE will, in turn, report each violation as required to assure notification to NTIA and DOC and the appropriate EPA Regional Office. | Please Select | Add any comment here (if required)
E. Procurement of Recovered Materials. In the performance of this Agreement, Respondent, and its subcontractors, if any, shall make maximum use of products containing recovered materials that are EPA-designated items, unless the product cannot be acquired — 1. Competitively within a timeframe providing for compliance with the contract performance schedule; 2. Meeting contract performance requirements; or 3. At a reasonable price. Information about this requirement, along with the list of EPA-designated items, is available at EPA’s Comprehensive Procurement Guidelines webpage: https://www.epa.gov/smm/comprehensive- procurement-guideline-cpg-program Respondent, and its subcontractors, if any, also agree to comply with all other applicable requirements of Section 6002 of the Solid Waste Disposal Act. | Please Select | Add any comment here (if required)
F. Prohibition on Contracting for Covered Telecommunications Equipment or Services. Respondent, and its subcontractors, if any, shall comply with 2 C.F.R. § 200.216, as applicable. As such, Respondent, and its subcontractors, if any, are prohibited from obligating or expending funds received from C SPIRE to: 1. Procure or obtain; 2. Extend or renew a contract to procure or obtain; or 3. Enter into a contract (or extend or renew a contract) to procure or obtain equipment, services, or systems that uses covered telecommunications equipment or services as a substantial or essential component of any system, or as critical technology as part of any system. As described in Public Law 115-232, Section 889, covered telecommunications equipment is telecommunications equipment produced by Huawei Technologies Company or ZTE Corporation (or any subsidiary or affiliate of such entities). i. For the purpose of public safety, security of government facilities, physical security surveillance of critical infrastructure, and other national security purposes, video surveillance and telecommunications equipment produced by Hytera Communications Corporation, Hangzhou Hikvision Digital Technology Company, or Dahua Technology Company (or any subsidiary or affiliate of such entities). ii. Telecommunications or video surveillance services provided by such entities or using such equipment. iii. Telecommunications or video surveillance equipment or services produced or provided by an entity that the Secretary of Defense, in consultation with the Director of the National Intelligence or the Director of the Federal Bureau of Investigation, reasonably believes to be an entity owned or controlled by, or otherwise connected to, the government of a covered foreign country. | Please Select | Add any comment here (if required)
G. Domestic Preferences for Procurements. As appropriate, and to the extent consistent with law, Respondent, and its subcontractors, if any, should, to the greatest extent practicable, provide a preference for the purchase, acquisition, or use of goods, products, or materials produced in the United States as described in 2 C.F.R. § 200.322 and Executive Order 14005. This includes, but is not limited to iron, aluminum, steel, cement, and other manufactured products. 2 C.F.R. § 200.321 provides that: “Produced in the United States” means, for iron and steel products, that all manufacturing processes, from the initial melting stage through the application of coatings, occurred in the United States; and “Manufactured products” mean items and construction materials composed in whole or in part of non-ferrous metals such as aluminum; plastics and polymer-based products such as polyvinyl chloride pipe; aggregates such as concrete; glass, including optical fiber; and lumber. | Please Select | Add any comment here (if required)
H. Secure and Trusted Communications Networks Act. Neither Respondent, nor its subcontractors, if any, may use grant funds received under the Middle Mile Grant Program to purchase or support any covered communications equipment or service (as defined in Section 9 of the Secure and Trusted Communications Networks Act of 2019 (47 U.S.C. § 1608). | Please Select | Add any comment here (if required)
I. Contracting with Small and Minority Businesses, Women’s Enterprises, and Labor Surplus Area Firms. Respondent, and its subcontractors, if any, shall take all necessary affirmative steps described in 2 C.F.R. § 200.321 to utilize minority businesses, women’s business enterprises, and labor surplus area firms when possible. | Please Select | Add any comment here (if required)
J. The Copeland Anti-Kickback Act. Respondent, and its subcontractors, if any, shall comply with all provisions of the Copeland Anti-Kickback Act (18 U.S.C. § 874), as applicable, which prohibits a person or organization engaged in a Federally supported project from enticing an employee working on the project from giving up part of their compensation under an employment contract. | Please Select | Add any comment here (if required)
K. Executive Order 13043. Respondent, and its subcontractors, if any, are encouraged to enforce on-the-job seat belt policies and programs when operating company-owned, rented, or personally owned vehicles, throughout the term of the Agreement. | Please Select | Add any comment here (if required)
L. Protection of Whistleblowers. Respondent, and its subcontractors, if any, will inform their respective employees in writing, in the predominant native language of its workforce, of their rights and remedies under 41 U.S.C § 4712 (Protections for Whistleblowers). | Please Select | Add any comment here (if required)
M. Disclosure of Violations of Federal Criminal Laws. In accordance with 2 C.F.R. § 200.113, Respondent, and its subcontractors, if any, must disclose, in a timely manner, in writing to C SPIRE all violations of Federal criminal law involving fraud, bribery, or gratuity violations potentially affecting the NTIA and DOC grant award received by C SPIRE, being NTIA Award No. 28-40-MM712, so that C SPIRE may timely disclose such violations to NTIA and DOC. | Please Select | Add any comment here (if required)
N. Applicable Environmental Requirements. Respondent acknowledges, and shall cause its subcontractors to acknowledge, if any, that it is Respondent’s responsibility to read, understand, and comply with all Federal and State environmental laws, regulations, Executive Orders, rules and standards to the extent such laws, regulations, Executive Orders, rules and standards may be applicable to Respondent and or its subcontractorsunder this Project. Such environmental laws, regulations, Executive Orders, rules and standards, include, but are not limited to, the following: 1. The National Environmental Policy Act of 1969 (42 U.S.C. §§ 4321, et seq.), as amended, including Executive Order 11514; 2. Section 106 of the National Historic Preservation Act of 1966 (16 U.S.C §§ 470f, et seq.), as amended; and 3. The Endangered Species Act (16 U.S.C. §§ 1531, et seq.), as amended; and 4. Any other Federal law or Executive Order listed in the DOC Financial Assistance Standard Terms and Conditions (November 12, 2020), as amended. Link: https://www.commerce.gov/oam/policy/financial-assistance-policy | Please Select | Add any comment here (if required)
O. Rights to Inventions Made Under a Contract or Agreement. Respondent, and its subcontractors, if any, shall comply with the requirements of 37 C.F.R Part 401, “Rights to Inventions Made by Nonprofit Organizations and Small Business Firms Under Government Grants, Contracts and Cooperative Agreements,” and any implementing regulations issued by DOC, as applicable. | Please Select | Add any comment here (if required)
P. Build America, Buy America Act. Respondent, and its subcontractors, if any, shall comply with all domestic content procurement preferences and other requirements to the extent applicable, specifically including the requirements that all fiber optic glass and fiber optic cable used in the Project be produced in the United States, pursuant to the Investment and Jobs Act, 2021, Pub. L. No. 117-58, 135 Stat. 429 (Nov. 15, 2021), including the Build America, Buy America Act, Pub. L. No. 117-58, §§ 70901-52 (BABA), as well as guidance provided by Memorandum for Heads of Executive Departments and Agencies, Initial Implementation Guidance on Application of Buy America Preference in Federal Financial Assistance Programs for Infrastructure, Executive Office of the President, Office of Management and Budget (April 18, 2022) (OMB M-22-11). Please note that NTIA has waived the Buy America domestic content procurement preference requirement for all iron, steel, manufactured products, and construction materials used in connection with this Project, with the exceptions of fiber optic glass and fiber optic cable. See Limited Applicability Nonavailability Waiver of the Buy America Domestic Content Procurement Preference as Applied to Recipients of Middle Mile Grant Program Awards, which was issued by the Assistant Secretary of Commerce for Communications and Information on April 18, 2023 and is accessible at: https://www.commerce.gov/oam/build-america-buy-america. | Please Select | Add any comment here (if required)
Q. Unanticipated Discoveries. Respondent, and its subcontractors, if any, shall comply with the procedures outlined below, in addition to applicable Federal, State, and local laws, in the event that a cultural resource is discovered. 1. Recognizing Cultural Resources A cultural resource discovery could be prehistoric or historic and includes archeological materials and human remains. Examples may include the following: • An accumulation of shell, burned rocks, or other food related materials; • Bones or small pieces of bone; • An area of charcoal or very dark stained soil with artifacts; • Stone tools or waste flakes (i.e., an arrowhead, or stone chips); • Clusters of tin cans or bottles, logging or agricultural equipment that appears to be older than 50 years; and • Buried railroad tracks, decking, or other industrial materials. When in doubt, it will be assumed that the discovered material is a cultural resource. 2. On-Site Responsibilities STEP 1: STOP WORK. If any employee, contractor or subcontractor believes that he or she has uncovered any cultural resource at any point in the project, all work adjacent to the discovery must stop. The discovery location should not be left unsecured at any time. STEP 2: NOTIFY MONITOR. If there is an archaeological monitor for the project, notify that person. If there is a monitoring plan in place, the monitor will follow its provisions. STEP 3: NOTIFY PROJECT MANAGEMENT: Project Manager or their designee will make all other calls and notifications. If at any time human remains are uncovered, they are to be treated with dignity and respect at all times. The remains will be covered with a tarp or other available material and are not to be covered with soil or rocks. This is for temporary protection to shield them from being photographed. The media is not to be notified or spoken to about the discovery of human remains. 3. Further Contact and Consultation A. Project Manager’s Responsibilities: • Protect Find: The Project Manager is responsible for taking appropriate steps to protect the discovery site. All work will stop in an area adequate to provide for the total security, protection, and integrity of the resource. Vehicles, equipment, and unauthorized personnel will not be permitted to traverse the discovery site. Work in the immediate area will not resume until treatment of the discovery has been completed following provisions for treating archaeological/cultural material as set forth herein. • Direct Construction Elsewhere On‐site: The Project Manager may direct construction away from cultural resources to work in other areas prior to contacting the concerned parties. • Contact Local Programs Archaeologist: If the Local Programs Archaeologist has not yet been contacted, the Project Manager will do so. If human remains are discovered on Federal or Tribal lands, then: stop all activity that may disturb the remains; immediately notify law enforcement or the district medical examiner; leave the bones and nearby items in place; and contact the County Coroner. The County Coroner will examine the remains within two working days, if he or she determines that the remains are Native American, they will notify the Native American Heritage Commission within 24 hours. The Native American Graves Protection and Repatriation Act (NAGPRA) of 1990 governs the return of Native American remains, funerary objects, sacred objects, and objects of cultural patrimony. NAGPRA applies to Federal or Tribal lands and requires Federal agencies and Native American Indian Tribes to protect Native American human remains or cultural items. B. Local Programs Archaeologist Responsibilities: • Identify Find: The Local Programs Archaeologist will ensure that a qualified individual examines the find to determine if it is archaeological. • If it is determined not archaeological, work may proceed with no further delay. • If it is determined to be archaeological, the Project Manager will continue with notification. • If the find may be human remains or funerary objects, the Project Manager will ensure that the Alabama Historical Commission (AHC) State Physical Anthropologist examines the find. If it is determined to be human remains, the procedure will be to notify AHC and Local Law Enforcement Agencies. 4. Proceeding With Construction Project construction outside the discovery location may continue while documentation and assessment of the cultural resources proceed. The Local Programs Archaeologist whether it be from AHC, a Tribe, or another professional consultant, must determine the boundaries of the discovery location. In consultation with AHC and affected Tribes, the Project Manager and the Local Programs Archaeologist will determine the appropriate level of documentation and treatment of the resource. The Federal agency(s) will make the final determinations about treatment and documentation. Construction may continue at the discovery location only after the process outlined herein is followed and the Local Programs Archaeologist (and the Federal agency(s)) determines that compliance with all Federal and State laws has been completed. | Please Select | Add any comment here (if required)
R. Civil Rights and Nondiscrimination Compliance. Contractor, and its subcontractors, if any, hereby acknowledge, that no person in the United States may, on the ground of race, color, national origin, handicap, age, religion, or sex, be excluded from participation in, be denied the benefits of, or be subject to discrimination under, any program or activity receiving Federal financial assistance, which includes this Project. As such, Contractor, and its subcontractors, if any, shall comply with the nondiscrimination requirements set forth in the following legal authorities, to the extent applicable, and hereby acknowledge that failure to do so may result in the cancellation of the Contract with Contractor and/or recoupment of any funds already disbursed to Contractor: (1) Title VI of the Civil Rights Act of 1964 (42 U.S.C. § 2000d et seq.) and DOC implementing regulations, published at 15 C.F.R. Part 8; (2) Title IX of the Education Amendments of 1972 (20 U.S.C. § 1681 et seq.); (3) The Americans with Disabilities Act of 1990 (42 U.S.C. § 12101 et seq.); (4) Section 504 of the Rehabilitation Act of 1973, as amended (29 U.S.C. § 794), and DOC implementing regulations, published at 15 C.F.R. Part 8b; (5) The Age Discrimination Act of 1975, as amended (42 U.S.C. § 6101 et seq.), and DOC implementing regulations, published at 15 C.F.R. Part 20; (6) Title VII of the Civil Rights Act of 1964, 42 U.S.C. § 2000e et seq.; (7) Parts II and III of Executive Order 11246, Equal Employment Opportunity (30 Fed. Reg. 12319), which requires that federally assisted construction contracts incorporate and fulfill the nondiscrimination provisions of §§ 202 and 203 of Executive Order 11246 and Department of Labor regulations implementing Executive Order 11246 (41 C.F.R. § 60-1.4(b)).; (8) Executive Order 13166, Improving Access to Services for Persons with Limited English Proficiency (65 Fed. Reg. 50121); (9) Executive Order 13798, Promoting Free Speech and Religious Liberty, and Office of Management and Budget, M-20-09 – Guidance Regarding Federal Grants and Executive Order 13798 (January 16, 2020); and (10) Any other applicable non-discrimination law(s). | Please Select | Add any comment here (if required)
II. CERTIFICATIONS
A. Certifications Regarding Debarment and Suspension - Instructions for Lower Tier Participant Certification 1. By submitting this proposal and accepting federal funding, the prospective lower tier participant is providing the certification set out below and agrees to comply with the requirements of 2 C.F.R. Parts 180, 1200, and 1326. 2. The certification in this clause is a material representation of fact upon which reliance was placed when this transaction was entered into. If it is later determined that the prospective lower tier participant knowingly rendered an erroneous certification, in addition to other remedies available to the federal government, the department or agency with which this transaction originated may pursue available remedies, including suspension or debarment. 3. The prospective lower tier participant shall provide immediate written notice to the person to which this proposal is submitted if at any time the prospective lower tier participant learns that its certification was erroneous when submitted or has become erroneous by reason of changed circumstances. 4. The terms covered transaction, civil judgment, debarment, suspension, ineligible, participant, person, principal, and voluntarily excluded, as used in this clause, are defined in 2 C.F.R. Parts 180, 1200, and 1326. You may contact the person to whom this proposal is submitted for assistance in obtaining a copy of those regulations. 5. The prospective lower tier participant agrees by submitting this proposal that, should the proposed covered transaction be entered into, it shall not knowingly enter into any lower tier covered transaction with a person who is proposed for debarment under 48 C.F.R. Part 9, Subpart 9.4, debarred, suspended, declared ineligible, or voluntarily excluded from participation in this covered transaction, unless authorized by the department or agency with which this transaction originated. 6. The prospective lower tier participant further agrees by submitting this proposal that it will include the clause titled “Instructions for Lower Tier Participant Certification” including the “Certification Regarding Debarment, Suspension, Ineligibility and Voluntary Exclusion- Lower Tier Covered Transaction,” without modification, in all lower tier covered transactions and in all solicitations for lower tier covered transactions and will require lower tier participants to comply with 2 C.F.R. Parts 180 and 1200. 7. A participant in a covered transaction may rely upon a certification of a prospective participant in a lower tier covered transaction that it is not proposed for debarment under 48 C.F.R. Part 9, Subpart 9.4, debarred, suspended, ineligible, or voluntarily excluded from the covered transaction, unless it knows that the certification is erroneous. A participant is responsible for ensuring that its principals are not suspended, debarred, or otherwise ineligible to participate in covered transactions. To verify the eligibility of its principals, as well as the eligibility of any prospective lower tier participants, each participant may, but is not required to, check the System for Award Management Exclusions website (https://www.sam.gov). 8. Nothing contained in the foregoing shall be construed to require establishment of a system of records in order to render in good faith the certification required by this clause. The knowledge and information of a participant is not required to exceed that which is normally possessed by a prudent person in the ordinary course of business dealings. 9. Except for transactions authorized under paragraph e of these instructions, if a participant in a covered transaction knowingly enters into a lower tier covered transaction with a person who is proposed for debarment under 48 C.F.R. Part 9, Subpart 9.4, suspended, debarred, ineligible, or voluntarily excluded from participation in this transaction, in addition to other remedies available to the federal government, the department or agency with which this transaction originated may pursue available remedies, including suspension or debarment. Certification Regarding Debarment, Suspension, Ineligibility and Voluntary Exclusion - Lower Tier Covered Transactions 1. The prospective lower tier participant certifies, by submission of this proposal, that neither it nor its principals is presently debarred, suspended, proposed for debarment, declared ineligible, or voluntarily excluded from participating in covered transactions by any federal department or agency. 2. Where the prospective lower tier participant is unable to certify to any of the statements in this certification, such prospective participant shall attach an explanation to this proposal. | Please Select | Add any comment here (if required)
B. Certification Regarding Lobbying. Respondent shall submit the certification below to C SPIRE as required by 31 U.S.C. § 1352. The undersigned certifies, to the best of his or her knowledge and belief, that: (1) No Federal appropriated funds have been paid or will be paid, by or on behalf of the undersigned, to any person for influencing or attempting to influence an officer or employee of an agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with the awarding of any Federal contract, the making of any Federal grant, the making of any Federal loan, the entering into of any cooperative agreement, and the extension, continuation, renewal, amendment, or modification of any Federal contract, grant, loan, or cooperative agreement. (2) If any funds other than Federal appropriated funds have been paid or will be paid to any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with this Federal contract, grant, loan, or cooperative agreement, the undersigned will complete and submit Standard Form-LLL, “Disclosure of Lobbying Activities,” in accordance with its instructions. (3) The undersigned will require that the language of this certification be included in all subcontracts and that all subcontractors shall certify and disclose accordingly. (4) The undersigned will file a disclosure form at the end of each calendar quarter in which there occurs any event that requires disclosure or that materially affects the accuracy of the information contained in any disclosure form previously filed by the undersigned pursuant to Paragraph (2) above. | Please Select | Add any comment here (if required)
This certification is a material representation of fact upon which reliance was placed when this transaction was made or entered into. Submission of this certification is a prerequisite for making or entering into this transaction imposed by section 31 U.S.C. § 1352. Any person who fails to file the required certification will be subject to a civil penalty of not less than $10,000 and not more than $100,000 for each such failure.
By signing below, ____________________________________ (the "Respondent") provides certifications, assurances, and representations for (1) the Certification Regarding Debarment and Suspension; and (2) the Certification Regarding Lobbying. In addition, the Contractor understands and agrees that the provisions of 31 U.S.C. § 3801, et seq., apply to this certification and disclosure, if any.
______________________________________________________ (CONTRACTOR) By: __________________________________________________ Witness: __________________________________________________ _______________________________, ________________ _______________________________, ________________ Print Name and Authorized Agent Title Print Name and Authorized Agent Title Contactor Mailing Address: ________________________________________________ City, State, Zip Code: ____________________________________ Telephone Number: _____________________________________ Email Address: _____________________________________________________________

## 9. Subcontractor Reporting
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Subcontractor Reporting RFP Number: MMG050725_Inspection Services
Respondent Name:
* This report must be completed and emailed to tc-grantsupport@cspire.com in its entirety by the 5th calendar day of each month.
A. Subcontracted Entities Information
SUBCONTRACTED ENTITY | As stated in the MM NOFO, if a recipient has not provided a certification that a project either will use a unionized project workforce or included a project labor agreement, meaning a pre-hire collective bargaining agreement consistent with section 8(f) of the National Labor Relations Act (29 U.S.C. 158 (f)), then the recipient must provide a project workforce continuity plan.
Please provide the name(s) below of any subcontracted entities performing work on the project, and the total number of workers employed by each entity.
| Name of Subcontracting Entity Performing Work | Total Number of People within this Subcontract | Job Categories of Workers Supporting Project within this Subcontract | Active | Please describe below the steps taken to ensure that workers on the project receive wages and benefits sufficient to secure an appropriately skilled workforce in the context of the local and regional labor market.

## 10. Workforce Reporting
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Workforce Reporting RFP Number: MMG050725_Inspection Services * This report must be completed and emailed to tc-grantsupport@cspire.com in its entirety by the 5th calendar day of each month.
A. GENERAL INFORMATION
GENERAL | Recipient Organization: | TROY CABLEVISION, INC. DBA C SPIRE | [8 empty] | Project Identification Number:
| Recipient Street Address: | 1006 S. BRUNDIDGE STREET | [8 empty] | Report Date (MM/DD/YYYY):
| City, State, and Zip Code: | TROY, AL 36081-3121 | [8 empty] | Final Report: |  |  |  |  | Yes | FALSE | No | TRUE
| Email: | tc-grantsupport@cspire.com
| Contract Organization: | [9 empty] | Report Period Start Date (MM/DD/YYYY):
| Contract Street Address: | [9 empty] | Report Period End Date (MM/DD/YYYY):
City, State, and Zip Code:
| Name and Title of Person Completing Report: | [9 empty] | Email and Phone No. of Contact
B. Workforce
DAVIS-BACON ACT CERTIFICATION | For projects receiving over $5,000,000 (based on expected total cost), as determined by the U.S. Secretary of Labor by subchapter IV of chapter 31 of title 40, United States Code (commonly known as the "Davis-Bacon Act"), all laborers and mechanics employed by contractors and subcontractors in the performance of such project are paid wages at rates not less than those prevailing.
Davis-Bacon Act Certification
| Does the recipient have access to the information requested (all laborers and mechanics employed by contractors and subcontractors in the performance of such project are paid wages at rates not less than those prevailing?) | [9 empty] | Yes | FALSE |  | No | FALSE | Davis-Bacon Certification For projects receiving over $5,000,000 (based on expected total cost), as determined by the U.S. Secretary of Labor by subchapter IV of chapter 31 of title 40, United States Code (commonly known as the "Davis-Bacon Act"), all laborers and mechanics employed by contractors and subcontractors in the performance of such project are paid wages at rates not less than those prevailing. Does the recipient have access to the information requested (all laborers and mechanics employed by contractors and subcontractors in the performance of such project are paid wages at rates not less than those prevailing?)
LOCAL HIRE PRIORITIZATION AND IMPACT | Local Hire Prioritization and Impact
Local hiring is a goal or requirement to hire people who live close to the place of work. This aim is often more specifically structured as a requirement for contractors awarded certain types of publicly funded projects to recruit a certain proportion of the people working on the project from a particular area. Please provide all direct hires and contractors supporting the MM Infrastructure project.
Please use the table below to describe how the project prioritizes local hiring.
| Hires by Race, Ethnicity and Gender | Number of Hires
Race/Ethnicity
|  | Hispanic or Latino |  |  | Non-Hispanic/Non-Latino | [17 empty] | Totals
[5 empty] | Men | [5 empty] | Women | [5 empty] | X
|  | Men | Women | X | White | Black or African American | Native Hawaiian or Pacific Islander | Asian | Native American or Alaska Native | Two or More Races | White | Black or African American | Native Hawaiian or Pacific Islander | Asian | Native American or Alaska Native | Two or More Races | White | Black or African American | Native Hawaiian or Pacific Islander | Asian | Native American or Alaska Native | Two or More Races
| Number of Local Direct Hires | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Non-Local Direct Hires | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Percentage of Local Direct Hires on Award | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Number of Local Subcontractors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Non-Local Subcontractors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Percentage of Local Subcontractors on Award | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
DAVIS-BACON WAGES | Davis-Bacon Act Wages
Please confirm if wages are at least prevailing*
*As stated in the MM NOFO as determined by the U.S. Secretary Labor in accordance with subchapter IV of chapter 31 of title 40, United States Code (commonly known as the "Davis-Bacon Act"), for the corresponding classes of laborers and mechanics employed on projects of a character similar to the contract work in the civil subdivision of the State (or the District of Columbia) in which the work is to be performed.
| Are wage rates at least the Davis-Bacon prevailing wage for all laborers? |  |  |  | Yes | FALSE | No | FALSE | Are wage rates at least the prevailing wage for all mechanics? | [6 empty] | Yes | FALSE | No | FALSE
| Please cite your source of how this information was gathered. | [7 empty] | Please cite your source of how this information was gathered.
If you answered "No" to either 10a. or 10c., please provide an attachment reporting the wages and benefits of workers on the project by job classification, and whether those wages are less than the prevailing wage.
WORKFORCE DEMOGRAPHICS | Workforce Demographic Data
| Jobs by Race, Ethnicity and Gender | Number of Jobs
Race/Ethnicity
|  | Hispanic or Latino |  |  | Non-Hispanic/Non-Latino | [17 empty] | Totals
[5 empty] | Men | [5 empty] | Women | [5 empty] | X
|  | Men | Women | X | White | Black or African American | Native Hawaiian or Pacific Islander | Asian | Native American or Alaska Native | Two or More Races | White | Black or African American | Native Hawaiian or Pacific Islander | Asian | Native American or Alaska Native | Two or More Races | White | Black or African American | Native Hawaiian or Pacific Islander | Asian | Native American or Alaska Native | Two or More Races
| Jobs Created | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Jobs Retained | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIONIZED WORKFORCE | Does this project include some workforce elements that are unionized? |  |  |  | Yes | FALSE | No | FALSE | Does your MM project utilize a project labor agreement? | [6 empty] | Yes | FALSE | No | FALSE
| Are workers provided access to union educators/organizers on employer property or during the work day? |  |  |  | Yes | FALSE | No | FALSE | Did workers receive additional information or training about their workplace rights in addition to already required notice postings? | [6 empty] | Yes | FALSE | No | FALSE
C. Attestation and Certification
By signing this report, I certify to the best of my knowledge and belief that the report is true, complete, and accurate for performance of activities set forth in the terms and conditions of my award. I am aware that any false, fictitious, or fraudulent information, or the omission of any material fact, may subject me to criminal, civil or administrative penalties for fraud, false statements, false claims or otherwise.
Typed or Printed Name and Title of Authorized Certifying Official: | [11 empty] | Telephone (area code, number and extension):
Email Address:
Signature of Certifying Official:
Date:

## 11. Evaluation Criteria
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Evaluation Criteria RFP Number: MMG050725_Inspection Services
Respondent Name:
- The C Spire evaluation team will assess each submitted proposal and rank the proposal according to the following point system:
Please note that no additional rounds of negotiations will take place. Kindly ensure that you submit your best and final pricing offer below
Counties Impacted | Autauga, Baldwin, Barbour, Bullock, Chambers, Chilton, Choctaw, Clarke, Coffee, Conecuh, Coosa, Covington, Dallas, Elmore, Escambia, Greene, Hale, Henry, Houston, Lee, Macon, Marengo, Monroe, Montgomery, Perry, Russell, Shelby, Tallapoosa, Washington, and Wilcox Counties.
Verify whether the proposal meets the threshold requirements outlined in RFP and it's Attachments. If the RFP does not meet the standards stop here, no further rating will be considered. |  |  | Please Select
Contract Pricing |  |  | 40
Availability of Staff & Equipment |  |  | 25
Company Attributes:
Minority Participation |  |  | 3
Value Add |  |  | 3
Location |  |  | 4
Financial Availability |  |  | 10
References |  |  | 5
Past Experience |  |  | 10
|  |  | 100 | 0
Rating Certification:
Rater's Signature: |  |  |  |  | Date:
Rater's Signature: |  |  |  |  | Date:
Rater's Signature: |  |  |  |  | Date:
Bid Status: | Award | Please Select |  | Additional Notes:
| Non-Award | Please Select
| Withdrawn | Please Select
SAMPLE

## 12. Aerial -Daily Report
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Aerial Daily Report RFP Number: MMG050725_Inspection Services
Below is the template for the 'Daily Report':
C SPIRE AERIAL DAILY REPORT
Date: |  | Project Name: |  | Project Number: | County / Franchise: | Preparer:
Weather Conditions:
Description of today's activities:
Strand ftg |  | Guys Set |  | Wreckout |  | Crew
Trunk Fiber | O-Lash/Lash | Anchors Set |  | De/Re
Feeder Fiber | O-Lash/Lash | Risers |  | Tree Trim
Blow Fiber |  | Bonds |  | De/Re
Pole Transfers |  | Pulled in Fiber |  | Delash
Make Ready |  | Drops Installed
Poles Set
Departed Office: |  | Arrived at jobsite: |  | Lunch out: | Lunch in: | Departed jobsite:
Accidents (Circle One): |  | No | Yes | If yes, complete Damage Reporting Form
Description:
Any Visitors / Inspectors?
On Site Equipment (Active or Idle)
Equipment ID | Beginning Hours/Miles |  | Description Of Use |  |  | Ending Hours/Miles
Materials Used
Units | Description |  |  |  |  | Cost | Delivered/Received by:
Issues
State below any problems encountered, remarkable occurrences, solutions to problems, supplementary comments.

## 13. UG -Daily Report
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Underground Daily Report RFP Number: MMG050725_Inspection Services
Below is the template for the 'Daily Report':
C SPIRE UNDERGROUND DAILY REPORT
| Cspire |  |  |  |  | Daily Fiber Report
Job Title:_______________________________________________________ | [5 empty] | Date:________________________________________
Town: _________________________________________________________ | [5 empty] | Day: _________________________________________
Time: Full Day - _________ Half Day - ________ Delay Day - ________ | [5 empty] | Inspector: _____________________________________________
Fiber Ct | Print | Station # | Pipe | Tail | Print | Station # |  | Pipe | Tail | Loop
Terminal |  | Footage | Fiber Ct | Total |  | Fiber Ct | Total |  | Fiber Ct | Total
_____ x _____ |  |  | 432 |  |  | 144 |  |  | 48
_____ x _____ |  |  | 360 |  |  | 96 |  |  | 24
_____ x _____ |  |  | 288 |  |  | 72 |  |  | 12

## 14. Aerial Inspection Report
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Aerial Inspection Report RFP Number: MMG050725_Inspection Services
Below is the template for the Job Inspection Report:
C SPIRE AERIAL INSPECTION REPORT
Date: | Project Name: | Project Number: | County / Franchise: | Preparer:
Time Arrived On Site: | Time Departed Jobsite: | Contractor / Crew:
Map Pages / Description:
Aerial |  | Notes
Anchors in correctly
Anchors in before strand tensioning
Correct framing height
Strand tensioned correctly
Bolt length correct
Correct separationg with power/comm.
Fiber installed correctly
Fiber double lashed over roads & RR
Aerial duct double lashed
Bug nut & strap/spacer placement correct
Bonding correct
Fiber marker installed & visible
Trunk storage at correct locations
Trunk storage footage correct
Feeder loops at correct poles
Feeder loops correct length
Taps hung in correct places
Taps numbered correctly
Riser guards installed
Cables clipped abover riser guard
Post lash road/ground clearance correct
As Built maps correctly marked
Permits on job sit

## 15. UG Inspection Report
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Job Inspection Report RFP Number: MMG050725_Inspection Services
Below is the template for the Job Inspection Report:
C SPIRE UG INSPECTION REPORT
Date: |  | Project Name: | Project Number: |  | County / Franchise: | Preparer:
Time Arrived On Site: |  | Time Departed Jobsite: | Contractor / Crew:
Map Pages / Description:
| Underground |  |  | Notes
Cable / Pipe placement matches layout running line
Cable / Pipe at the correct depth
Method used to check depth
Ped placement matches layout
Vault placement matches layout
Rocks in Vaults
Ped placed correctly to bury line and square
Pipe placed correctly inside ped
Dirt fill inside ped correct
Correct amount of cable inside Ped
Correct amount of cable inside Vault
Ground rods in vault wih cases
Locate wires bonded correctly
Fiber markers placed matches layout
Fiber markers installed correctly
Locate markers bonded properly
Peds numbered correctly
Blowing equipment properly set up
Fiber "Figure 8" correct
Fiber pulling done correctly
As Built map correctly marked up
Permits on job site

## 16. Damage Reporting Form
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Damage Reporting Form RFP Number: MMG050725_Inspection Services
Below is the template for the Utility Damage Reporting Form:
Date of Damage to Underground Facility: (m/d/y) _____________________________________
City & County where damage occurred: _____________________________________________
Address where damage occurred: __________________________________________________
Time Damaged Occurred: ________________________________________________________
Time Damaged Repaired: ________________________________________________________
WHO DAMAGED THE FACILITY?
| Contractor - | Occupant -
| County Entity - | Railroad -
| Developer - | State Entity -
| Farmer - | Utility -
| Municipality - | Unknown -
Did they have a Locate (Ticket) Number? Yes________ No________
If yes, give the Locate (Ticket) Number: ______N/A________________
Were the Underground Facilities Located? Yes________ No________
If yes, were the underground facilities located correctly? Yes________ No________
CHECK TYPE OF UTILITY AFFECTED
| Cable TV - | Pipeline -
| Electric - | Telephone -
| Fiber - | Water -
| Gas - | Wastewater -
Other -
Did Damage cause an Interruption of Service? Yes________ No________
Estimated number of customers affected by the interruption? ____________
Was this a “Near Miss”? Yes________ No________ (A near miss is considered to be "no damage to the utility, but work was performed on the easement or facility without authorization, with no financial damage".)
CHECK RIGHT OF WAY WHERE DAMAGE OCCURRED
| Data Not Collected - | Public (City Street) –
| Dedicated Public Utility Easement - | Public (County Rd) -
| Federal Land - | Public (Interstate Hwy) -
| Pipeline - | Public (Other) -
| Power Transmission Line - | Public (State Hwy) -
| Private (Business) - | Railroad -
| Private Easement - | Unknown / Other -
Private (Landowner) -
CHECK TYPE OF EXCAVATION EQUIPMENT
| Auger - | Grader / Scraper -
| Backhoe / Track hoe - | Hand Tools -
| Boring - | Vacuum Equipment -
| Data Not Collected - | Probing Device -
| Drilling - | Trencher -
| Directional Drilling - | Unknown / Other -
Explosives -
CHECK TYPE OF WORK PERFORMED
| Agriculture - | Fencing - | Site Development -
| Blading - | Gas - | Steam -
| Bldg. Construction - | Irrigation - | Storm Drain/Culvert -
| Bldg. Demolition - | Landscaping - | Street Light -
| Cable TV - | Lot Grading - | Telecommunications -
| Curb / Sidewalk - | Petroleum Pipe - | Traffic Signal -
| Data Not Collected - | Pole - | Transmission Pipe -
| Drainage - | Public Transit Auth - | Water -
| Driveway - | Railroad Maint - | Waterway Improve -
| Electric - | Road Work - | Unknown/Other -
| Engineering/Survey- |  | Sewer -
DESCRIPTION OF INCIDENT:
_______________________________________________________________________________________________________________________________
PERSONNEL ON HAND:
1. Construction Crew
_______________________________________________________________________________________________________________________________
_______________________________________________________________________________________________________________________________
2. Utility repair crew
_______________________________________________________________________________________________________________________________
_______________________________________________________________________________________________________________________________
C Spire fiber Warehouse Locations
The Warehouse is located at
1006 S Brundidge Street, Troy AL 36081
Note on C83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add Enterprise Grant Warehouse

## 17. Signature Page
Troy Cablevision, Inc., d/b/a C Spire Middle Mile Broadband Infrastructure Grant (MMG) Program for Connect Alabama Project Inspection Services RFP, Signature Page RFP Number: MMG050725_Inspection Services
Undersigned, a duly authorized officer or agent of ________________________________ ("Respondent"), does hereby execute this Proposal as of the date listed below for and on behalf of Respondent, and as such, acknowledges and agrees that Respondent shall furnish the services described in this Proposal and shall be bound by all terms and conditions stated in this Proposal, including, but not limited to, all pricing terms described herein, unless otherwise mutually agreed upon in writing by Respondent and Troy Cablevision, Inc. d/b/a C Spire ("C Spire"). Respondent shall not change, amend, modify, or alter in any manner the terms or conditions of this Proposal, including, but not limited to, all pricing terms described therein, for a period of not less than ninety (90) days from the Proposal Due Date as defined in that certain Request for Proposal published by C Spire and dated the _______ of ___________________ 20___ (the "RFP"), in response to which Respondent submits this Proposal. Further, Respondent acknowledges and agrees that in the event this Proposal is successful and is conditionally awarded by C Spire to Respondent, then all applicable terms and conditions of this Proposal, including, but not limited to, all pricing terms described herein, shall be incorporated into the Services Agreement, a copy of which was provided by C Spire to Respondent in connection with the RFP, and shall be valid and binding for the entire term of the Services Agreement, as described therein. Respondent acknowledges that it must execute and fully comply with the Services Agreement and furnish all required performance and payment bonds to C Spire within ten (10) calendar days following receipt of notice by C Spire that this Proposal was successful (the "Award Period"). Respondent shall become the contractor with respect to the particular segment of the Project described in this Proposal following its execution of the Services Agreement and furnishment of all required performance and payment bonds to C Spire within the Award Period.
Respondent Name: | ________________________________________________
Respondent Address: | ________________________________________________
________________________________________________
License #: | ________________________________________________
Date: | ________________________________________________
By: | ________________________________________________
Name and Title of Authorized Officer or Agent
Signature: | ________________________________________________
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Uniform reference to: Master Services Agreement, Material Purchase Agreement, Construction Services Agreement